## Slide 1: FREIA – Tollgate 2 NSS status and meeting objectives
Shane Kennedy
NSS Project Leader
European Spallation Source ERIC
www.europeanspallationsource.se
31st January 2018

## Slide 2: The 15 NSS Project Instruments All are funded to be world leading in 2023
Instrument Class | Instrument | Costbook Value (M€) | Performance targets (@ 2MW)
Large Scale Structures | LOKI (Broad band SANS) | 12.19 | 5 x D22 & 20 x SANS2D
 | SKADI (General Purpose SANS) (+SONDE funds) | 11.50 | 4 x D22
 | ESTIA (Focusing Reflectometer) | 11.80 | Conventional mode: ~ 100 x D17 High intensity mode: 1cm2 samples = seconds
 | FREIA (Liquids Reflectometer) | 13.2 | 30 x FIGARO, INTER
Diffraction | DREAM (Bispectral powder diffractometer) | 13.66 | > 10 x POWGEN or WISH
 | HEIMDAL (Hybrid diffractometer) | 13.55 | ~ 50 x GEM, ~ 8 x new POLARIS
 | MAGIC (magnetism single crystal diffractometer) | 13.10 | Cold: > 100 x worlds best, Thermal: 1mm3 crystals = 10 min
 | NMX (Macromolecular crystallography) | 11.67 | > 10 x LADI & Biodiff
Engineering & Industrial | BEER (Engineering diffractometer) | 14.99 | world leading in strain scanning, unique flexibility
 | ODIN (multi-purpose imaging) | 11.60 | world leading for high resolution, > 10 x best for TOF methods
Spectroscopy | BIFROST (extreme environment spectrometer) | 13.45 | > 10 x THALES & MACS
 | C-SPEC (cold chopper spectrometer) | 16.50 | 100 x IN5 (w RRM)
 | T-REX (bispectral chopper spectrometer) | 16.85 | 3 x 4-SEASONS, 3 x IN5
 | VESPA (vibrational spectroscopy) | 12.0 | 10 x VISION (ΔE = 130 meV)
 | MIRACLES (backscattering spectrometer) | 13.53 | 2 x BASIS and DNA
Total cost book value |  | 199.59 | 
With a further ~ 56 M€ investment ESS will more than double the performance of these instruments:
ESS has submitted proposals to ESS/ERIC Council to fund or part/fund these upgrades

## Slide 3: Planned order of commencement of operation of first 8 instruments (August 2023)
Matching early success in delivery of scientific outputs with the capacity of Lead In-Kind partners to deliver on schedule (ISIS, PSI, FZJ, LLB, HZG/NPI, TUM/PSI, TUM/LLB & DTU lead consortium).
Instrument Class | Sub-class | Candidates
Large Scale Structures | Small Angle Scattering | LOKI (ISIS) or SKADI (FZJ)
 | Reflectometry | ESTIA (PSI) or FREIA (ISIS)
Diffraction | Powder Diffraction | DREAM (FZJ) or HEIMDAL (ÅU)
 | Single crystal diffraction | MAGIC (LLB) or NMX (ESS)
Engineering | Strain scanning | BEER (HZG/NPI)
 | Imaging and tomography | ODIN (TUM/PSI)
Spectroscopy | Direct Geometry | C-SPEC (TUM) or T-REX (FZJ)
 | Indirect Geometry | BIFROST (DTU), MIRACLES (Bilbao), VESPA (CNR)
Instruments in bold type to be operational by start of user program
Italic:
backups in case of delays

## Slide 4: NSS Neutron Instruments: Project scope -15 instruments + test beamline
ESS Instrument Layout (September 2017)
ESS In-Kind Partners also collaborate on sample environment, data management systems etc.
ESS Lead Partners for instrument construction
ODIN
DREAM
NMX
MIRACLES
T-REX
MAGIC
BIFROST
HEIMDAL
FREIA
LOKI
VESPA
ESTIA
SKADI
+
+
C-SPEC
+
Nuclear Physics Institute
BEER
Test Beam Line

## Slide 5: Instrument Milestones Phase 1 schedule

## Slide 6: Internal* Neutron Beam Instrument Schedule Draft for Discussion V3.4, 25th October 2017
NOTES:
Assumes 2MW maximum power until end 2025
Phases aligned with TG2 reviews on 1st 10 NBIs
Installation & Integration (TG4) + Hot Commissioning (TG5) for first 8 NBIs aligned with draft BOI plan (schedule match typically within 1 month)
Preliminary Design
Detailed Design
Manufacturing & Procurement
Installation & Integration
Hot Commissioning/Early science
Operation
Hot Comm.
instruments
West sector
North sector
East and South sectors
Current date
First access to NSS areas
Start User Program
Beam on Target
* still under discussion with ESS-ERIC Council
2016 2017 2018 2019 2020 2021 2022 2023 2024 2025
Current baseline – to be updated Q2 2018
Notes: This schedule assumes
  obtaining the radiological licenses in a timely fashion from SSM. A trigger ‘first optical instrument component outside the monolith’ and a 6 months period from submission of the application to obtaining the SSM license - have been assumed (pending formal confirmation from ESH).
  an initial hot commissioning of Accelerator and Target (A&T) to establish reliable beam on target at design frequency and pulse width.
In 2021, commissioning of the first (4-5) neutron instruments is to be conducted at low power, where possible, in order to minimize activation of in-bunker components of the neutron instruments. In the current plan, the duration of this initial commissioning period is 10-12 weeks.
Over 2022 and 2023 beam power and availability will increase, as the first 8 or more neutron instruments start hot commissioning, with a goal of reaching 2 MW source power by the start of the user program and maintaining that level until 2026.
Commencement of hot commissioning for the first 8 neutron instruments (TG5 in Table 1) is closely aligned with the schedules presented by those instrument build teams at TG2. This order matches well with the NSS “Early Science Success” strategy, and distributes responsibility for delivery widely among our experienced In-Kind partners. Changes to this order will be made if necessary to mitigate effects of delays to individual neutron instrument projects.
TG5 dates for neutron instruments 9-15 will be delayed to concentrate on-site resources for installation and commissioning (both cold commission and hot commissioning) on the first eight instruments to facilitate early science success for those instruments. This is discussed further below and illustrated in the NSS Installation and Commissioning schedule (Fig. 3).
TG3 dates refer to “final” approval of detailed design, when the integrated design of all major components is judged to be complete, and beyond which no further approval from NSS management is required for manufacturing. At this point in time these TG3 dates are not fixed, but NSS management plans for this to occur in staged manner. “Early procurement” approval dates for in-monolith optics and other critical path procurements (such as in-bunker components for the first instruments) are not shown in the figure

## Slide 7: Access Dates for NSS IK partners
E02
E03
E04
E05
E01
D06
D07
D08
1b
4
3
2
1a
2
E01 – Full Access 27-May-19 (incl. Crane)
1a
1b
E02 Area 1 – Partial Access 27-May-19
E02 Area 2 – Partial Access 15-Nov-19
D03 Main Hall – Partial Access 01-Dec-19 (incl. Cranes)
3
D01 Area 1 Main Hall – Partial Access 06-Feb-20
(incl. Cranes)
4
D01 Area 2 Main Hall – Partial Access 02-April-20
(incl. Crane)
5
Exact Location of Final De-Lineation Point TBC
5
D01
D03
D02
D05
D04
Hand-over dates from NSS Project to Instrument teams
Based on NSS –MS V3.4 (15 September 2017)
Current baseline – to be updated Q2 2018 after the ESS rebaseline

## Slide 8: First out-of-bunker access dates for Instrument Installation
E02 (1)
E01
D01
D03
D02
Nov 2019
December 2019
February 2020
April 2020
Jan-Jun 2021
Jan-Jun 2021
May –Nov 2021 (full D01 same date range)
Current estimation 30th Jan 2018
Re-baseline dates due
from CF/SEC late Feb -18
E03
E04
Jan 2020
Dec 2019
May 2019
Sep 2019
E02 (2)
✓

## Slide 9: First in-bunker access dates for Instrument Installation
D01
Aug 2019
May – Nov 2020
D02 Mar 2019 Jan 2020
D02
D03
Jun 2019
Feb - Aug 2020
D02 Feb 2019 Jan 2020
Start of joint work with Target in D02 (R6, NBOA & LS etc.) and start of bunker construction in D01 & D03
D01
Dec 2019 June 2021
D02
D03
Dec 2019 Sep 2021
Start of first in-bunker access for Neutron Instrument construction
1.
2.
12-17 months delay from CF/SEC plus 3-4 months extra time needed in bunker for joint TD/NSS work (i.e. NBOA, LS, plugs)
12-17 months delay from CF/SEC
Dates to be looked into further! Depends on TD and NSS!
Current estimation 30th Jan 2018

## Slide 10: NSS Floor loading limits: Reduced in D01 & D03 in February 17
Under the bunker (D02 & inner parts of D01 & D03); 30 t/m2
In the rest of D01 & D03
      In general (under guides & instrument caves); 14 t/m2
      Around perimeter (3 metres from wall); 10 t/m2
      Staging areas (near truck access doors); 20 t/m2
In E01 & E02 (long instruments in west sector); 20 t/m2
D04
D06
D07
D08
E03
E04
E05

## Slide 11: NSS provisions for FREIA (p. 1/2)
Local workshops and workshop support for on-site installation from early 2019
  Some workshops are likely to be off-site (in Lund) initially
Chemistry laboratories and sample handling facilities includes RML in D08 from 2020

## Slide 12: NSS provisions for FREIA (p. 2/2)
Sample Environment: NSS Sample Environment pool to include
  Gas Processing #1-2 (Q1/23)
  Julabo-type chiller/heater #1-3 (Q1/23)
  Injection system, syringe pump (Q1/23)
  Stopped flow systems (Q1/23)
  Rheometer (Q1/23)
  Solid-liquid & liquid-liquid cells (Q1/23)
  IR Furnace LATER
  Portable Laser heating LATER
  2.5T warm bore Cryomagnet #2 LATER
  5T warm bore Cryomagnet LATER
  Vacuum box LATER
  Stress/strain rig (generic) (possible)
Initial-Operations budget request to include:
  Julabo-type chiller/heater #4 (specific)
  Langmuir troughs (specific)
  Air-liquid troughs (specific)
  Overflow cylinder (specific)
  Laser interferometer alignment (specific)
  HPLC pump, 4 channel, switch (specific)
  Injection system, syringe pump (specific)
  Humidity Chamber (possible)
https://1drv.ms/x/s!AuCQb_HPf3b9g8g2HHqvybpQKix-Lg
Notes: Also in SAD list: flagged as externally funded:
  Reaction cells (Q1/25)
  In-situ light scattering (Q1/25)
  In-situ gas absorption (Q1/25)
  In-situ thermal analysis (Q1/25)

## Slide 13
Deliverables
Science case covering scientific relevance, impact and usage
Conceptual design with credible estimates of performance
Preliminary costing.
Proposal and Planning
Instrument Proposal
Phase 0
Preparation for Design
Deliverables
Conceptual design updates
Prototyping
Definition of facility requirements and interfaces
Clarification of institutional responsibilities
Resource planning
Deliverables
Scientific and technical requirements
Technical design concept
Delivery plan for all phases (including hot commissioning)
Delivery Schedule covering all phases
Resource plan
Staging plan for later enhancements
Budget with contingency at 10% of cost to complete
Phase 1
Preliminary Design
Design and Construction
Phase 2
Detailed Design
Phase 3
Manufacturing and Procurement
Deliverables
Complete definition of all major technical components
Completion of detailed plan for Phase 3
Refined plan for phase 4
Refined Resource plan
Refined delivery schedule, with critical path items and dependencies
Refined budget with contingency at 10% of cost to complete
Deliverables
Procurement and manufacture of all major technical components
Completion of detailed plan for phase 4
Site preparation
Refined plans for phase 5 and for staging
Refined Resource plan
Refine instrument delivery schedule
Maintain budget with contingency at 10% of cost to complete
Installation and Commissioning
Phase 4
Installation and Integration
Phase 5
Hot Commissioning
Deliverables
Construction of physical infrastructure on site.
Assembly and installation of technical components
Integration and testing of technical components
Installation, integration and testing of Personnel Safety System
Submission of application for approval to hot commission
Formal project completion
Deliverables
Verification of performance of Personnel Safety System
Proof of compliance with radiation dose limits
Critical performance demonstration of basic functionality
Scientific performance demonstration
Friendly user experiments
Completion of technical and user manuals
Tollgate 1
STAP review
SAC recommendation
NSS recommendation
STC approval
Tollgate 2 (PDR)
Preliminary Design Review
STAP review
NSS
scope review
assign cost book value
Approval by SD
Tollgate 3 (CDR)
Critical Design Review
STAP review
ICB review
NSS approval
Tollgate 4 (IRR)
Installation Readiness Review
ICB review
NSS approval
Tollgate 5 (SAR)
Safety systems acceptance review
NSS approval
Tollgate 6 (ORR)
Operations readiness review
NSS approval
NSS Project; Neutron Instrument project phases

## Slide 14: Tollgate 2 Process
TOLLGATE 2 MEETING: evaluation of
final technical design concept,
scientific scope,
project budget,
schedule and
resource plan
TOLLGATE 2 REVIEW possible outcomes:
No major problems: implement recommended changes and revise baseline documents, before moving instrument project into Phase 2 (< 3 months allowed).
Major problems: continue in Phase 1 and prepare for a second TG2 review (< 6 months allowed).
Review committee report submitted to Science Director within two weeks of TG2 meeting

## Slide 15: Objectives for this meeting
 scientific parameters -that it will meet the stated performance criteria,
 engineering -that it is feasible to build with all of the appropriate interfaces,
 safety and licensing -that it meets the requirements for safe operations and licensing
 budget -that it can be built within the budget,
 schedule -that it can be built and made ready for hot commissioning in the required timeframe
 management -that the instrument consortium has the capability and sufficient resources to deliver according to their plan.
 operation and maintenance – that it can be operated (incl. performing experiments using samples and sample environment) and maintained.
(ESS-0051706)

## Slide 16: Phase 2: detailed design (1/2)
Aim: To bring the design of the Neutron Instrument components to a state of readiness for Manufacturing and Procurement (M&P).
Essential achievements:
Complete detailed design of all major components coherently so as to minimize risk of incompatibilities and need for redesign work as the Project moves into Phase 3: M&P.
Detailed planning for M&P. Note Phase 2 does not include M&P.
Exception: where long lead-time procurements add considerable risk to project schedule.
Approval to begin early M&P: by NSS Project via Neutron Instruments Lead Engineer (Gabor Laszlo).
Detailed planning for Phase 4: Installation and Integration.
Technical Annex for whole of project to be completed within 3 months of Phase 2
Draft Template for the TA is available

## Slide 17: Phase 2: detailed design (2/2)
Notes on Phase 2:
Careful scheduling of Phases 3 & 4 ensures resource planning for M&P processes (e.g. FAT & SAT), site preparation, installation and system integration, cold commissioning activities and licensing processes.
Critical dependencies should be identified and a critical path analysis should be performed in this phase.
The NSS Construction Engineer will develop and maintain an integrated installation plan that takes into account the procurement schedules for all Neutron Instruments, CF building schedules, and resource allocation.
Instrument | Order | TG3 date (provisional) | First access to D/E | First Access to bunker | Priority access to bunker | TG5 – Hot Commissioning
FREIA | 15 | Dec-2019 | Jan-23 | Jun-23 | Jun-24 | Jan-25
Current dates based on MS 3.4
to be updated Q2 2018 after the ESS rebaseline

## Slide 18: NSS Project management
SSM application
Safety Systems analysis & design
Budgets & workflow
Schedule
Risk Management
Conventional Facilities
Systems Engineering
Neutron Bunker
Requirements & Standards
Target Project
Memoranda of Understanding
Technical Annexes
In-Kind Collaboration Agreements
Partner coordination
NMX (ESS)
HEIMDAL (ÅU)
MAGIC (LLB)
DREAM (FRJ)
LOKI (ISIS)
FREIA (ISIS)
SKADI (FRJ)
ESTIA (PSI)
ODIN (TUM/PSI)
BEER (HZG/NPI)
C-SPEC (TUM)
T-REX (FZJ)
BIFROST (DTU)
MIRACLES (ESS Bilbao)
VESPA(CNR)
Project Leader: Shane Kennedy
Deputy Project Leader: Oliver Kirstein
Neutron Instruments:
Lead Scientist: Ken Andersen
Lead Engineer: Gabor Laszlo
In-Kind Office:
Lead: Michela Del’Anno Boulton
Integration Activities:
Lead: Zvonko Lazic
Planning:
Lead: Sofie Ossowski
Safety and Licensing:
Lead: Arno Hiess
Director for Science
Andreas Schreyer
ESS Technical Board
Chair: Roland Garoby
Instrument Collaboration Board
Chair: Andreas Schreyer
Four Instrument Classes
Large scale structures
Engineering & imaging
Spectroscopy
Diffraction
Instrument Class Co-ordinator (scientist) assigned to each instrument

## Slide 19: NSS Project: Engineering Integration and Interface Management
Co-ordinate:
Instruments i/f to ESS, during construction
Physical installation & integration on site
Neutron Instruments
Peter Sångberg
Systems Engineering
Zvonko Lazic
PM Bunker
Antonio Bianchi
Construction
Co-ord
Gabor Laszlo
Instrument Co-ord
Bunker
- Bunker integration to instruments
- Bunker Design PM
- Design standards
- PIM alignment
- EPL alignment
Co-ordinate NT:
Gen. of Requirements
Prep. of Specifications
Ensure Parts commonality
Ensure Robust design
Ensure RAMI is implemented
Operations perspective
SE process & methodologies
Documents structure/consistency
Design Reviews (in acc. to SE)
Co-ordinate:
Instruments i/f to ESS, in design (Instruments=“Black boxes”
Ensuring consistency in information flow to Instrument Teams
External
i/f:
PSS
Shane Kennedy
NSS Project Leader
External i/f:
Site Infra-
structure
External i/f:
ESH
Helena Ramsing
Safety & Licensing
Michela Dell’Anno B
In-Kind
Mgmt
External i/f:
In Kind
Phil Bentley
Neutron Optics and
Shielding
Sofie Ossowski
Project Co-ord
Jörgen A/ Clement M
Planning
External
i/f:
ICS
Iain Sutton
Technical
Co-ord
External
i/f:
Target
Neutron
Technologies
Schedule Integration

## Slide 20: September/October 2017
Target
LINAC
West sector (160 m) Instruments
East sector Instruments
South sector Instruments

## Slide 21: Agenda for FREIA TG2 meeting