## Slide 1: ICS Status, plans and support
Henrik Carling
Head of ICS division
www.europeanspallationsource.se
2017-11-20

## Slide 2
Overview

## Slide 3: The ESS integrated control system
The ESS facility is a large and complex machine with very much and diverse equipment that needs to work in synchronization and with well-known configurations
For this purpose almost all equipment at the ESS facility is connected to the Integrated Control System
Examples:
  Voltage supplies for magnets
  Vacuum systems
  Cryogenic equipment
  RF equipment
  Air conditioning in the tunnel
The control system is the ”central nervous system of ESS”
An estimated 1.6 million control points will be needed

## Slide 4: ESS/ICS high level description
The Integrated Control System Division (ICS division) is responsible for the control systems within the ESS facility including controls for accelerator, target, neutron scattering systems and conventional facilities. In addition, ICS scope includes the ESS Machine Protection System and the ESS Personnel Safety System.
The control system size/complexity is very high: 1600 kPv
  Compared with: SNS 600 kPv, Diamond 2000 kPv, FRIB 400 kPv
Facility availability goals are very high - ICS plays a key role for availability
Some new approaches will be implemented at ESS/ICS
  Full scale deployment of EPICS 7
  Full scale deployment of MTCA.4 - new innovative technology
  Ambitious approach to automation of control system configuration
  High performance requirements on the MPS to ensure availability

## Slide 5: ICS Project scope
Work package 01 Management and administration
Work package 02 Software Applications
Work package 03 Software core
Work package 04 Hardware core
Work package 05 Machine protection
Work package 06 Equipment
Work package 07 Control system infrastructure
Work package 08 Physics
Work package 09 Personnel safety systems
Work package 10 Integration - Accelerator
Work package 11 Integration - Target
Work package 12 Integration - Instruments
Work package 13 Integration - Conventional facilities
Work package 14 Test Stands
Work package 20 Installation
Software
Electronics
Infrastructure
Safety & protection

## Slide 6: Group Structure - Safety and protection
Personnel Safety Systems work package 09:
Stuart Birch
Denis Paulic
Morteza Mansouri
Yong Kian Sin
Alberto Toral
Mattias Ericsson
Machine Protection work package 05:
Manuel Zaera-Sanz
Riccard Andersson
Szandra Kövecses
Enric Bargallo
Stephane Gabourin
David Sanchez
Viktor Fred
Machine Protection and Personnel Safety Systems Group
Group Leader: Annika Nordt
Deputy Group Leader: Denis Paulic
Goal: Build a flexible and strong team, sharing & extending the different skill sets,
Everyone has knowledge relevant for both MP and PSS!
MP and PSS will follow IEC61508.

## Slide 7: Scope of Machine Protection
Machine Protection helps in achieving the operational availability requirements for ESS. High availability is achieved through high system reliability, through short preventive and corrective maintenance times and short recovery times after stopping beam operation.
The right strategy to avoid damage leading to long corrective maintenance times, will involve a mix of:
dedicated technical systems stopping operation (not only of beam) to prevent and mitigate damage,
dedicated operational and maintenance procedures to fix things before real damage can occur.
Machine Protection needs to reliably do the following:
protect the “machine” from damage, be it beam-induced or resulting from any other source,
protect the “machine” from unnecessary beam-induced activation.
Machine protection will be implemented in a way to:
minimize unnecessary down-time due to spurious trips,
provide optimal support for failure localization,
support all operational modes of the facility,
support operation in degraded mode.
Notes: Text according to slide

## Slide 8: Scope of Personnel Safety Systems
The ESS Personnel Safety Systems are loosely divided into three major systems:
The Accelerator PSS,
The Target PSS,
The Neutron Instruments PSS (one system for each of the 22 Neutron Instruments).
The primary role of the ESS PSS is to prevent personnel from being harmed by exposure to ionizing radiation generated by the proton and neutron beams, under all operating modes.
The ESS PSS will also be used to control and mitigate against the following hazards inside pre-defined controlled areas:
Oxygen depletion (primarily from helium leak from the super conducting sections)
High voltage from assorted equipment
Radio frequency
X-Rays
Mitigation will be achieved by controlling access to the different areas when a potential hazard is present and switching off the equipment generating the hazards.
Notes: Text according to slide

## Slide 9: Group Structure - Infrastructure
Control System Infrastructure Group
Group Leader - Remy Mudingay
Work Unit 14.07.01
Control Room
Remy Mudingay
Work Unit 14.07.02
Data Centre
Alessio Curri
(System Administrator)
Work Unit 14.07.03
Control System Network
Susann Skarin
Johan Christensson
Work Unit 14.07.05
Infrastructure Applications
Benjamin Bertrand
ESS Staff
In-Kind partner
Contractor
Institute for Energy Technology:
S. Collier
M. Rosenqvist
P. Le Darz
Institute for Energy Technology
Terje Bordal
Thor-Egil Ekeli
System Administrator
(Vacant)
Tallinn Institute of Technology
Dr Andro Kull
Dr Rain Ottis –
Dr Hayretdin Bahşi
Dr Olaf Maennel
Dr Risto Vaarandi
Peter Holgersson
Fredrik Luthander
Anders Harrisson
Control Room
Equipment
Cybersecurity

## Slide 10: Control System Infrastructure Scope
The group’s responsibilities are to Design, Implement and Operate the IT Infrastructure needed to reliably run the Experimental Physics Industrial Control System (EPICS) eco-system. The main activities can be grouped into two parts:
Main Control Room/Data Centre and Networks - The activities include responsibility over the design, installation, configuration and maintenance where applicable:
Human factors analysis and ergonomic design of the ESS Main Control Room.
File and storage services for data produced by the machine for ‘on-line’ and ‘off-line’ analysis.
A secure Technical Network that interconnects the private machine networks for Accelerator, Cryogenics, Neutron Instruments, Target and Utilities (electrical substations and HVAC) to operation consoles located in Control rooms.
Control System Software authorisation tools and services.
Software Infrastructure – The activities include responsibility to design, install, configure and maintain the supporting applications for control specific software development.
Integration services for software development life-cycle for EPICS software.
Software Development environment
Configuration management and software deployment.
Monitoring tools and services of Software applications used to configure the control system.

## Slide 11: Group Structure - Hardware and integration
Hardware and Integration Group
Acting group leader: Henrik Carling
Work package manager: 04, 10, 14
Embedded systems (MTCA , FPGA, Linux)
Angel Monera
Simone Farina
Oliver Talevski
Mehdi Mohammednezhad
EPICS Integration
David Brodrick (work package 12)
John Sparger
Jeong Han Lee
William Ledda
Faye Chicken
Tomasz Brys
Joao Paulo Martins
Krisztian Löki
Saeed Hagthtalab
Thomas Fay
Automation
Benedetto Gallese (work package 11)
Francois Bellorini
Peter van Velze
Miklos Boros
Motion Control
Julen Etxeberria
Timing System
Javier Cereijo
Upcoming recruitments
  3 positions
  1 or 2 consultants - project management
Other
Nour Akel - Installation coordinator

## Slide 12: Controls System Integration
The systems under the scope of the Hardware and Integration Group span over 20 buildings, out of a total of 35 in the complex:
Accelerator Control Systems (G01, G02)
Target Control Systems (D02)
Instrument Control Systems(D01-D08, E01-E05)
Site Infrastructure Control Systems (H01, H05, H06)
Hardware and Embedded software Systems (B02)
The Hardware and Integration Group is in charge of the design , installlation, maintenance, support of the Integrated Control System. For the sake of this presentaion ‘Integrated Control System’ refers to the following 5 subsystems:
  Hardware and Embedded software Systems (work package 04)
  Accelerator Control Systems (work package 10)
  Target Control Systems (work package 11)
  Instrument Control Systems (work package 12)
  Conventional Facilities Control Systems (work package 13)
  Test Stands (work package 14)

## Slide 13: Hardware and Integration Responsibilities
The scope of the hardware and integration group cover 5 big control systems, which are composed of a big number of subsystems:
    Hardware and Embedded software Systems
    Accelerator Control Systems
    Target Control Systems
    Instrument Control Systems
    Site infrastructure Control Systems
The Hardware & Integration Group shall provide control system integration to all relevant ESS stakeholders (Accelerator, Target, Site Infrastructure, Neutron Instruments).
Integration Support is defined as: the effort provided by ICS that is required for deploying the control system components, which provide monitoring and control functionality to the stakeholder systems.
The integration support includes among others:
    Design of the different control systems and integration in the overall ICS
    Development, upkeep and maintenance of (~500+) IOCs software in the plant
    Development and standardization of hardware technologies: mTCA infrastructure, DAQ Systems, PLCs, etc.
    Troubleshooting and support to operators (on-call) service
    Providing ESS with necessary infrastructure for management of EPICS modules, FPGA firmware, PLC Code etc.
    Support other Divisions with EPICS, PLC programming and FPGA development know-how.

## Slide 14: Group Structure - Control System Software
Control System Software Group
Group Leader:
Susanne Regnell
work package 08 Physics:
Emanuele Laface
Juan F. Esteban Müller
Ben Folsom (Ph.D Student)
work package 03 Software Core Components:
Karin Rathsman
Jan-Åke Persson
Ricardo Fernandes
Claudio Rosati
Georg Weiss
Banafsheh Hajinasabi
Fredrik Söderberg
+ Off-site consultants

## Slide 15: Scope ICS/Control System Software
Providing control system software applications, providing the following services:
EPICS Control System Studio:
  Operator screens
  Data browser
  Probe
  Archiver (Archiver Appliance)
  Alarms system (BEAST)
  Channel Finder functionality
  Save, Compare & Restore functionality (MASAR)
Post Mortem service/application
Calibration service/application
Diagnostics service/application
Generic information screens
Controls Configuration (ESS Named devices, cables)
Open XAL* framework with Physics online model

## Slide 16
Organizational plans

## Slide 17
ESS ERIC BOARD OF DIRECTORS DIRECTOR GENERAL
MACHINES DIRECTORATE
SCIENCE DIRECTORATE
ACCELERATOR
TARGET
PROJECT SUPPORT & ADMINISTRATION DIRECTORATE
CONVENTIONAL FACILITIES
HUMAN RESOURCES
GENERAL SERVICES
SCIENTIFIC PROJECTS
SCIENTIFIC ACTIVITIES
NEUTRON TECHNOLOGIES
NEUTRON INSTRUMENTS
INTEGRATED CONTROL SYSTEM
DATA MANAGEMENT SOFTWARE CENTRE
ENGINEERING & INTEGRATION SUPPORT
FINANCE
INFORMATION TECHNOLOGY
LEGAL
SUPPLY, PROCUREMENT & LOGISTICS
ES &H and Q
COMMUNICATIONS & EXTERNAL RELATIONS

## Slide 18: ICS Organization 2017-11
Henrik Carling
Division head
Anna Gillberg
Team assistant
Annika Nordt Safety and protection
Hector Novella
Deputy project manager
Susanne Regnell
Controls Software
Timo Korhonen Chief engineer
Emanuele Laface
Accelerator physicist
Juan Esteban Müller
Software scientist
Ricardo Fernandes Control system software architect
Claudio Rosati
Software engineer
Javier Cerejo PhD Student
Angel Monera
FPGA Engineer
David Sanchez
Automation engineer
Manuel Zaera-Sanz
Lead engineer slow interlocks
Morteza Mansouri
Safety systems engineer
Riccard Andersson Technical coordinator
Stuart Birch Senior engineer
Ben Folsom
PhD student
Temporary employee
Employee
Consultant
Consultant off-site
Joao Martins
Integrator
Benedetto Gallese
Integrator
Yong Kian Sin IEC61508 engineer
François Bellorini
Integrator
David Brodrick
Integrator
Position under consideration
Mehdi Mohammednezhad
Integrator
Jeong Han Lee Integrator
Consultants
Julen Etxeberria
Junior controls engineer
Open positions (3)
Saeed Haghtalab Integrator
Krisztián Löki
Integrator
Alessio Curri System administrator
Karin Rathsman Accelerator scientist
Fredrik Luthander
Software engineer
Wojtek Fabianowski in-kind manager
Jan-Åke Persson
Senior software engineer
Benjamin Bertrand
Software engineer
Remy Mudingay
Controls infrastructure
Oliver Talevski
Embedded engineer
Susann Skarin Network administrator
Alberto Toral
Technician
Thilo Friedrich
Systems engineer
Enric Bargalló
Lead analyst engineer
John Sparger
Integrator
William Ledda
Integrator
Miklos Boros
Integrator
Maria Romedahl
Technical coordinator
Szandra Kövecses Lead integrator
Manorma Kumar
PSS analyst
Stephane Gabourin Lead engineer fast interlocks
Viktor Fred Lead engineer electrical installations
Denis Paulic
DGL, PLC engineer
Mattias Eriksson
Technician
Fredrik Söderberg
Software engineer
Open positions (2)
Faye Chicken
Technician
Peter van Velze Technician
Nour Akel
ICS Installation coordinator
Simone Farina Embedded systems egineer
Georg Weiss Software engineer
Banafsheh Hajinasab
Software engineer
Open position
(Henrik Carling acting)
Start 2018-01
Start 2017-12
Tomasz Brys
Integrator
Thomas Fay
Integrator
Open positions (1)
Start 2017-11
Johan Christensson
Infrastructure technology engineer
Anders Harrisson
Software configuration manager
ESS-0081625
Peter Holgersson
Electriocal engineer

## Slide 19: Organizational development - ICS
Recruitments almost concluded
  Controls infrastructure group -> ”done”
  Controls software group -> ”done”
  Hardware and integration group -> 3 more to go (below)
  Safety and protection group -> 1 ongoing - 1 more to go
  Management team -> 1 ongoing (below)
Replacement for Daniel Piso
  Candidate selected
  Next step is MBL (union) negotiation scheduled for 2017-11-23 -> moved to 2017-11-24
  Offer to be given 2017-11-27 -> I expect fast reply to offer
Consultant(s) for project management
  Procurement process ongoing 12 - 24 month contract
  Project manager for work package 10
  Possibly one additional project manager consultant to support work packages 04, 09, 11, 13, 14 and 20
Hardware and integration: one recruitment concluded
  Saeed Haghtalab - starting 2018-01-08
  Three remaining positions - no advertisement now
Controlling function -> Diana Bergenholz

## Slide 20: Integration services framework and other procurements
Hardware and integration framework
  Commercial framework agreement to significantly improve and simplify ICS’ procurement
  Process has been very long and cumbersome - but now finally completed
  About 20 suppliers in seven lots (more than one lot for some suppliers)
  Supplier kick-off meeting 2017-12-04
    EPICS-based control system integration engineering services
    Embedded systems integration engineering services
    Industrial/process systems integration engineering services
    Control systems infrastructure integration engineering services
    Control systems safety related integration engineering services
    Control systems technical and installation services
    Integration project administration, management and training services
Procurement initiative MTCA - ”Procurement for innovation” project to start
  A BrightnESS/European Commission funded initiative to unify ”big sience customers”
  Purpose is to drive innovation among MTCA manufacturers
  Project lifetime 2017-11 - Q1 2018
  Benefit for ESS: Long term strengthening of MTCA market case
  ”Normally urgent” procurement will continue in parallel with this initiative

## Slide 21: Technology scope for ICS (end of 2017)
The overwhelming majority of value within ICS’s scope is represented as manual labor
The span of technical scope and competencies needed in ICS is very wide
From analog signals to Java-based high-end, big-data GUI:s in high performance, high availability
PLC systems; Safety and protection systems
Infrastructure: networking, data centre, control room
Systems integration, Installation
Project management and administration
Electronics hardware
Software
PLC
Infrastructure
Analog electronics
Digital electronics
FPGA firmware
Digital communication
PCB, packaging
Test and validation
Industrialization, maintenance
Kernel drivers
Operating systems (RT)
Development environments
EPICS
CSS/Eclipse
Applicatoins (GUI, Web, Services)
Databases
Availability, performance
Test and validation
Safety and protection
In-house
External
In-kind

## Slide 22
Status and planning

## Slide 23: Current focus areas Disclaimer: not priority - just intensity
High intensity areas
  Alignment with target division on project processes and responsibilities
  Assisting/participating in integration in in-kind projects
  Construction and installation of PSS0 for commissioning of Ion source and LEBT
  Deployment and improvements to ESS EPICS environment
  Deployment of ICS standard electronic platform (full stack)
  Deployment of control system configuration tool family
  ICS Contributions to SSM warm linac trial operation permit application
  Installation and deployment of PSS systems for ODH
  Installation and deployment of control system infrastructure
  Normal intensity areas
  Systematic development of machine protection
  Control systems for “industrial process” systems
  Development of calibration service
  Development of instrument controls
  Deployment and maintenance of cable database, naming service…
  Assisting/participating in integration in in-kind projects
  Beam physics application development
  Improving/organizing ICS laboratories and test stands
  Participating/driving community level topics such as EPICS 7 and MicroTCA

## Slide 24: Planning for Beam instrumentation
  Based on input from beam instrumen-tation, ICS has analyzed the need for controls hardware platform configurations
  ICS has defined a set of hardware ”recipes” that is used as the planning basis when it comes to procurement and budgeting for hardware (including in-kind contributions)

## Slide 25: Planning for Beam instrumentation
ICS has now almost completed the recruitment of permanent staff
A integration services framework will be available since 2017-12
Some smaller in-kind opportunities may be still open for 2018
To allocate resources for beam instrumentation, planning and prioritization input is neccessary

## Slide 26
Detailed status (2017-11)

## Slide 27
ICS work package 03: Software
27
  Achievements
  "Visual Style Guide" document progressing
  Channel Finder (e.g. setting up client server for Elastic Search) progressing
  Calibration service: Build the HDF5 64-bit library for Mac
  CCDB, Cable DB, IOC Factory, Naming service commonality, integration and user support work ongoing
  Visited Cosylab with to take over responsibility for CCDB, Cable DB and IOC Factory
  Logbook (elog) deployed
Issues
  Currently no resource to work with the Archiver.
  Next steps
  Finalise and release the first version of the "Visual Style Guide" document (Nov 8th)
  Getting the ESS Channel Finder version up and running
  Define Calibration template in Nexus files together with Tobias Richter
  Continue working with the CCDB ecosystem (commonality, integration and user support)
  CS-studio support and bugfixes, improve the display builder, implement widgets
  Structure and clean up the Software pages in Confluence.
We are making progress, but much is yet to do.

## Slide 28: ICS work package 04: Hardware Core
Focus still on EEE and MTCA
Achievements
  Ongoing work with EEE (evaluating issues)
  Driving MTCA crates and related equipment procurement started
  Issues
  VAT issue with PSI in Switzerland blocks procurement progress
  IOxOS documents should be synchronized with deliveries
  Next steps
  Continue works on IFC1410/20, ADC311X, DIO3118, Struck 8300KU for RF-LPS, LLRF, BLM, and generic subsystems
  Continue works on EEE (mrfioc2, devlib2, require, epics bases, and so on).

## Slide 29: ICS work package 05: Machine Protection
Achievements
Many line activities, ICALEPCS, ARW, PhD dissertation …
Clarity on protection system test-stand lab at Medicon Village; space requirements for site lab has been provided
New cable procurement in place and prepared connector procurement in parallel
Issues
Budget balance for installation. Viktor Fred to help on more detailed estimations.
Its difficult to define in detail the interfaces to machine protection for the warm linac;
  In particular there is a difference between the ISRC + LEBT test-stand installation and the installation for warm linac commissioning
Next steps
Clarify and document interfaces with ISRC, LEBT, MEBT and DTL equipment.
Prepare electrical design for ISRC, LEBT, RFQ, MEBT, DTL MP systems and relevant connections and relevant procurement.
Test possible interface implementations to connect PLC based interlock systems to the Fast Beam Interlock System
Good progress at the moment. But budget issues.

## Slide 30: ICS work package 07: CS Infrastructure
Achievements
  Detailed progress and status update of the local control room has been communicated/presented to AD
  Progress on issues regarding EEE delivery to INFN, in-kind partner, in Italy
Issues
  Nothing to remark.
Next steps
  LCR installation to complete before 2017-11-24
  Collaboration with DMSC for CUB server room design procurement service - tender will be published by ESS procurement by 2017-11-10
  Travel to IFE, Norway to;
    officially close IK network project
    update on on-going 2 IK projects (Compute and MCR stage 2)
    plan for upcoming IK project (MCR stage 3).
  Assist in network installation planned to be conducted by Coromatic AB next week.
Many deadlines still to meet

## Slide 31: ICS work package 08: Physics
Achievements
  Open XAL / elog integration ongoing
  Python course continuing (8 out of 10 lectures done)
  Jupyther hub and elog is progressing
  Major achievement for Cavity model, requested help from the RF group to access cavity shape data
Issues
  New logbook implementation has been resource intensive/expensive
    Possible re-prioritization needed when we plan to replace the logbook in the future
Next steps
  Integrate elog and Open XAL into Jupyther hub scripting environment
  Continue working with the new Cavity model
  Evaluation of cavity re-phase mechanism (potentially paper for IPAC)
  Change installer mechanism for Open XAL; artifactory
Good progress for the cavity model

## Slide 32: ICS work package 09: Personnel Safety Systems
Achievements
  All ODH installation (phase 1) except PLC racks installed
  ODH racks are currently being built at ProcessKontroll
  Sole source for PSS0 installation injected into Procurement system
  PSS0 drawings and documentation 50% complete
  PSS1 Analysis continuing
Issues
  Stub design appears to going backwards
    The PSS requirements where shared with the Stub team in October 2016 and again in September 2017 now it seems that our requirements have been ignored.
Next steps
  Complete PS0 documentation
  Complete ODH documentation
  Complete PSS1 documentation for SSM
Requirements for the stubs have to be retransmitted

## Slide 33: ICS work package 10: Accelerator integration
Lack of resources impacting progress
Achievements
  Driver for digital I/O FMC DIO3118 released on the IFC1410 platform. Data acquisition with IFC1410, ADC3117 and DIO3118 verified
  Significantly improved TOSCA framework driver received from in-kind partner PSI. Integration of driver in existing platform started
  Standardized MicroTCA platform packages prepared. First deliveries to beam instrumentation and in-kind partners CEA and ESS Bilbao
  Jira task assignment for the ICS hardware and integration team - that has been blocked for a long time - has now resumed
  Coordination of installation of ICS equipment in the “stubs” - which connect from the klystron gallery to the accelerator tunnel - started
  EPICS pvAccess/services procurement concluded. Selected supplier to start working immediately enhancing EPICS 7 functionality
  Roll-out of industrial automation version and configuration management tool - VersionDog - started. Stakeholder introductions will be held
Issues
  Lack of resources.
Next steps
  Support on DTL in terms of Beckhoff and Simens HW
  Continuous works on pending activities on the RFQ and MEBT control system.
  Continuous works on Vacuum control programming, documents, and configuration.
  Accelerate progress on the planned procurement of Micro TCA crates and related electronics and define a procurement roadmap

## Slide 34: ICS work package 11: Target integration
Deep issues with interface definitions to stakeholders.
Delay in the schedule;
Achievements
  CMS LOMP analysis almost finalized, but it needs another iteration
  CMS functional analysis document (draft version) matches expectations
  Procurement for the PLC network equipment is done
Issues
  CMS LOMP contains incorrect information
  Not possible to fulfill the hardware standardization due to equipment purchased by Target before the interfaces definition: ==>big impact on the reliability of the system
Next steps
  CMS hardware configuration and (process control) equipment estimation;
  beginning of the electrical design (process control equipment) for CMS;

## Slide 35: ICS work package 12: Instruments integration
Work on ESTIA, DREAM and ODIN is progressing
Achievements
  Software/timing development for chopper controls. Nearly ready for HZB.
  Fixed problems with HV power supply IOC.
  Good progress on syringe pump IOC.
  ESTIA SEMP circulated for informal review. Good progress on ESTIA requirements document.
  Met with DREAM team and organising meeting with ODIN.
  Present sample environment control strategy at Scientific Activities Division technical meeting.
Issues
  Some replanning/prioritisation needed for 2018
Next steps
  Detector readout workshop.
  Vertical integration at HZB.

## Slide 36: ICS work package-13 CF integration week 1745
Achievements
  Collaboration with ABB for the integration of the Power Scada is ongoing
  G04 HVAC system integration progressing slowly
Issues
  Nothing to report
Next steps
  Keep on with the collaboration with ABB to solve the integration with the Power Scada related to all the electrical substations (like H05, H06, G04)
  Continue working on G04 integration
Very slow progress

## Slide 37: ICS work package 14: Test Stands Integration
Missing service organization to support partners
Achievements
  Nothing to highlight
Issues
  Not enough resources to support test stands (FREIA, teststand2, LTH)
Next steps
  Continue working on the configuration for the ICS vertical test stands.

## Slide 38: ICS work package 20: Installation
ICS installation progress from 2017-10-30 – 11-03
ICS installations on-going coordination with the FEB stakeholders
On-going coordination with Coromatic, safety inductions planned
ICS discussed and coordinated cable ladders usage regarding network infrastructure scope for G02 cold box hall and G04 with Cryo
Work and Safety Coordination Plan for Coromatic AB update approved [ESS-0181706].
CSI - G02 - Method statement and JHA for switch installation in COMMs room C approved [ESS-0149332].
Issues
Cryo control room non-conformity in the ceiling is within CF/SEC process flow, waiting AccSys to grant safe access, risk of delay for the commissioning of the cryoplants.
Local control room equipment poorly covered, chance of
getting damaged during on-going CF works over there.
Current state of the LCR:
Next steps from 2017-11-06 – 11-17
ICS installations on-going coordination with the FEB
stakeholders
Coromatic first installations of data and communications
cables to take place
Installation slowing down

## Slide 39
In-kind status

## Slide 40: ICS in-kind portfolio development
ICS has been expanding the in-kind potential value by identifying and publishing new scope for possible partner contribution
Sometimes in-kind expansion occurs as natural extensions of prior in-kind activities
When analyzing the total in-kindable scope in the plan, we currently seem to see a limit at ~21 M€

## Slide 41: ICS In-kind partners
Agreement signed
Agreement waiting for signature
Early discussions
Collaboration/other agreement
Partner Institutes
Atomki, Hungary
CEA, France
CNRS/IPNO, France
Elettra, Italy
ESS Bilbao, Spain
IFE, Norway
INFN Catania, Italy
INFN Legnaro, Italy
PSI, Switzerland
STFC, UK
Tallinn Technical University, Estonia
ÚJV Řež, Czech Republic
University of Łódź , Poland
Uppsala University, Sweden
ZHAW, Switzerland

## Slide 42: ICS in-kind status
  PSI: Good progress - software and firmware deliveries made - volume deliveries expected 2018-03
  TUT: Ethercat: HW-prototype - delayed. FPGA-IOC: delayed. Cyber security: On track
  IPNO: Discussions ongoing. Signed TA slated for IKRC 14
  CEA: Starting work on the RFQ controls. Discussing how to handle nBLM
  ESS Bilbao: MEBT controls project progressing
  ZHAW: On track - good progress.
  INFN Legnaro: No contract yet. Work has started nevertheless
  IFE: MCR: On track, Software (Logbook/Alarms): On track, Procurment (Network/Compute): On track
  Rez: No activities <- Closed
  Atomki: No activities
  STFC: Several (smaller) TA:s defined but high-level agreement missing
  Łódź: Agreement signed. Work to start 2018-01. Preparations (nBLM have already begun)

## Slide 43
Support

## Slide 44: Reference Persons per Technology
Each technology or area of expertise has a reference person.
He/She has the most knowledge about and is the goto person for that.
He/She will sustain the vision of ICS with respect to a specific technology.
He has an overview of use cases for that technology
He/She is aware of issues related to a technology and to drive the finding of solutions..
This person is not the only one that knows how to use a specific technology or does all the work associated with it. The tasks that are related to these technologies probably fall mostly into WP4.
Technology/Speciality Reference Person
Motion control David Brodrick, Jeong Han Lee
Timing system Alexander Soderqvist
FPGA n. a.
IFC (IOxOS) Jeong Han Lee
ESS EPICS Environment Jeong Han Lee
MTCA4 Infrastructure - Firmware (MCH,Power Module, Cooling Unit) Jeong Han Lee & Timo Korhonen.
PLC Nick Levchenko
s7plc (EPICS Device Support, IOC ,OPI) Nick Levchenko
d-tacq(Linux Kernel Driver, EPICS Device Support, IOC ,OPI) Niklas Claesson
ADC 3110(Linux Kernel Driver, EPICS Device Support, IOC ,OPI) Niklas Claesson
ADC 3170(Linux Kernel Driver, EPICS Device Support, IOC ,OPI) n. a.
Struck (Linux Kernel Driver, EPICS Device Support, IOC ,OPI) Niklas Claesson (Linux Kernel Driver, EPICS Dev. Support), Alexander Soderqvist (IOC,OPI)
AreaDetector (EPICS Device Support, IOC ,OPI) Alexander Soderqvist
Not updated since 2016

## Slide 45: Reference Persons per Subsystem/Discipline
Each subsystem has also a reference person.
He/She sustains the vision of ICS with respect to integrating that subsystem into the control system.
He/She is proficient with the relevant technologies.
He/She is the primary point of contact for that subsystems/discipline.
He has an overview of all running subsystems .
The person does not do all the work related to integrating a subsystem.
Technology/Speciality Reference Person
Vacuum Controls Francois Bellorini
Cryogenics Systems Benedetto Gallese
Beam instrumentation Jeong Han Lee
RF LLRF RF LPS Jeong Han Lee
Target Diagnostics Jeong Han Lee
RF Reference Line Alexander Soderqvist
NSS David Brodrick
Target Benedetto Gallese
Conventional facilities Nick Levchenko
Main Power Supply Nick Levchenko
Water Cooling Nick Levchenko
PS & LEBT Integration Nick Levchenko
RFQ, DTL, Spokes, Elliptical Daniel Piso
Lab Management David Brodrick
Magnets & Power Supplies n. a.
Not updated since 2016

## Slide 46: Areas that need reinforcement in the short/medium term
Technology/Speciality Reference Person
Motion control David Brodrick, Jeong Han Lee
Timing system Alexander Soderqvist
FPGA n. a.
IFC (IOxOS) Jeong Han Lee
ESS EPICS Environment Jeong Han Lee
MTCA4 Infrastructure - Firmware (MCH,Power Module, Cooling Unit) Jeong Han Lee & Timo Korhonen.
PLC Nick Levchenko
s7plc (EPICS Device Support, IOC ,OPI) Nick Levchenko
d-tacq(Linux Kernel Driver, EPICS Device Support, IOC ,OPI) Niklas Claesson
ADC 3110(Linux Kernel Driver, EPICS Device Support, IOC ,OPI) Niklas Claesson
ADC 3170(Linux Kernel Driver, EPICS Device Support, IOC ,OPI) n. a.
Digital IO n. a.
Struck (Linux Kernel Driver, EPICS Device Support, IOC ,OPI) Niklas Claesson (Linux Kernel Driver, EPICS Dev. Support), Alexander Soderqvist (IOC,OPI)
AreaDetector (EPICS Device Support, IOC ,OPI) Alexander Soderqvist
StreamDevice (EPICS Device Support, IOC, OPI)
Technology/Speciality Reference Person
Vacuum Controls Francois Bellorini
Cryogenics Systems Benedetto Gallese
Beam instrumentation Jeong Han Lee
RF LLRF RF LPS Jeong Han Lee
Target Diagnostics Jeong Han Lee
RF Reference Line Alexander Soderqvist
NSS David Brodrick
Target Benedetto Gallese
Conventional facilities Nick Levchenko
Main Power Supply Nick Levchenko
Water Cooling Nick Levchenko
PS & LEBT Integration Nick Levchenko
RFQ, DTL, Spokes, Elliptical Daniel Piso
Lab Management David Brodrick
Magnets & Power Supplies n. a.
Not updated since 2016

## Slide 47: Support from ICS hardware and integration group
The group has grown dramatically from 2 employees/6 consultants 18 months ago to 15 employees/6 consultants (and three remaining open positions)
The highly complex matrixed organization devised for the hardware and integration group needs to be revisited
With a new group leader we have the opportunity to shape smaller, agile teams that better can serve integration tasks
Eventually (2018) the hardware and integration group will be split in two groups. There are several models for this but this has not yet been concluded

## Slide 48
Back-up

## Slide 49
MicroTCA infrastructure and platform

## Slide 50: Control system infrastructure components
MTCA.4
  Crates, MCH, Cooling Units, PSU
I/O and processing
  Digital platforms
Timing System
  EVG, EVR, Distribution System
Motion control
  EtherCAT/Beckhoff
  EtherCAT master in (MTCA) EPICS IOC, no extra (Beckhoff) PLC required for simple (no complicated coordination) axes.

## Slide 51: MTCA base infrastructure
MTCA.4 crates in two variants
  6-slot, 3U crate
    For smaller, more distributed systems (saves rack space)
    Cooling and airflow issues with first prototype
      Front-to-rear cooling is challenging due to small air inlet area
      Added one fan to improve airflow (loud!)
  12-slot, 9U crate
    For systems that can utilize many slots
    Has been in use, stable configuration
  MCH (Micro Channel Hub) from N.A.T.
Specification-wise ready for series procurement

## Slide 52: MTCA Crate variants
3U, 6-slot crate
4 slots with place for rear transition module
CPU, EVR in remaining slots
9U, 12-slot crate
12 slots with place for rear transition module
2 MCH slots (redundancy)
4 PSU slots

## Slide 53: IFC_1410 AMC: FMC carrier with CPU
Two High-Pin Count FMC slots
  80xLVDS, GTHx4 (x2 with KU060)
Kintex UltraScale FPGA (KU040 or KU060)
  1 GByte of SDRAM directly attached
    2 banks – for dual buffering
  4-lane PCIe Gen3 to MTCA backplane
Freescale QoriQ T2081 CPU
  4 cores hyperthreaded (8 virtual)
  E6500 core with dual-precision FPU and Altivec
TOSCA-III Firmware library
  Full source code available
  PCI Express switch (non-transparent)
  Supports all features of the card

## Slide 54: Digital platforms, status and support
IFC_1410 (and IFC_1420)
  In-kind contribution from PSI (boards + firmware + software)
    Generic packages of firmware, drivers, EPICS support
  Project had delays due to slow start of in-kind
    Also ramp-up of internal resources
  Development done with ICS cash injections
    Not optimal but hardware is now in good shape
    Tried to shuffle with a 10-unit initial batch between developers and users
    PSI support was limited until full approval
  But now: strong support from PSI
    1 FPGA engineer, 1 SW engineer full time
    Part-time support of 7 more people (controls, LLRF, instrumentation)
    Use of PSI resources for ADC performance characterization, etc.
    Production-quality kernel drivers (initial) release
  Series production has started
    First batch (25+25 IFC_1410 units) mid-November

## Slide 55: Digital platforms, status and support
IFC_1410 (and IFC_1420)
  Firmware status
    Generic applications (“oscilloscope”) running since a while
    ICS has been working on RF support (RF-LPS firmware), highest priority
  Drivers (Linux, kernel)
    Worked so far on a version from the commercial partner
    This had a number of issues: thread safety, etc.
    A new, production-quality driver, supported by PSI and commercial partner released (yesterday)
      Few details to be finalized
  EPICS
    Moving support to the new driver
    Area Detector will be the main driver for ESS
    Also a generic driver from PSI will be supported (regDev). This is primarily for prototyping but has also been used in production.
      Like “streamDevice” but for register-based, memory-mapped devices
      No programming needed
IFC_1410 demo at ICALEPCS ‘17 conference in Barcelona, two weeks ago
Generic “oscilloscope” firmware
250 MSPS ADC
Running EPICS (3.15.4)
CS-Studio GUI

## Slide 56: System characterization report available

## Slide 57
Timing infrastructure

## Slide 58: Timing system
MRF Event System
  Tree-topology trigger and data distribution
    Master node, synchronized to RF (88 MHz)
    Arbitrary number of receivers
  MTCA.4 receiver with backplane trigger and clock support
    Supports also backplane triggers and clocks. Also standalone operation
Master Event Generator
RF Master Oscillator
fanout
Event
receiver
88 MHz
fanout
Event
receiver
Event
receiver
Event
receiver
Event
receiver
Event
receiver
Event
receiver
Event
receiver

## Slide 59
ESS EPICS Environment
(EEE)

## Slide 60: EPICS support
ESS EPICS Environment
  Based on a concept that has been successfully used at PSI for >10 years
    Pre-compiled drivers dynamically loaded at IOC start
    Enables better management of driver base
  ESS version has suffered from a few issues
    Dependency handling caused problems
      Over-ambitious in trying to automatize – got too complex
    Upstream modules (from EPICS community) do not always follow same versioning rules
      Sometimes API changes between minor versions
    Issues with version tagging and continuous integration
      Triggered un-intended updates
  Project was orphaned for a while (personnel changes)
    Effort has now been put in support – still new though
    Problem causes have been understood and fixes found – WIP
Even with the above issues, this got us successfully through the PS&LEBT commissioning in Catania
  With remote development and some support visits

## Slide 61: ICS vision and mission statements
ICS vision statement
ESS operated efficiently, reliably and safely, with a control system that everyone loves
ICS mission
The ICS division shall provide and maintain world-class and cost-efficient control, protection and safety systems and services for the ESS facility.
The division shall develop competence and innovative solutions that can be shared in the community through open processes