## Slide 1: Controls for TS2 Cryomodule Testing System Review
Wojtek Fabianowski
Integrated Control Systems
ESS/ICS
2017-11-30

## Slide 2: Test Stand 2 – ICS planning and activities
Outline
  ICS scope
  Resource situation/organization
  Collaboration
  Schedule/planning
  Areas of attention – modulator, RF, LLRF

## Slide 3: ICS contribution to TS2
ICS involvement at test stand 2
    Controls infrastructure (Technical network, Timing, Control room)
    RF local protection system
    Personnel safety system
    LLRF system
    Cryo distribution system, Valve box
    Vacuum Controls
Other activities
    Machine protection system (to be tested later in future, not planned for TS2)

## Slide 5: Control Architecture and Process
High-level controls (EPICS)
Low-level controls (PLC, MTCA)

## Slide 6: Process Control Architecture picture taken from ESS-0099046..ICD between ICS-processand Test Stand 2

## Slide 7: Resources and Staff – ESS and Partners
ESS ICS
IPNO
CEA

## Slide 8: ICS Resources
Maria Romedahl
Technical coordinator
Henrik Carling
Head of Division
Anna Gillberg
Team assistant
Safety and protection
Annika Nordt
Hector Novella
Deputy project manager
Controls Software
Susanne Regnell
Timo Korhonen Chief engineer
Emanuele Laface
Accelerator physicist
Juan Esteban Müller
Software scientist
Ricardo Fernandes Senior software engineer
Claudio Rosati
Software engineer
Javier Cereijo PhD Student
Alberto Toral Diez
Technician
Denis Paulic
Deputy Group Leader
Manuel Zaera-Sanz
PLC Engineer
Morteza Mansouri
Safety Engineer
Riccard Andersson Technical Project Coordinator
Stuart Birch Senior safety engineer
Ben Folsom
PhD student
Joao Paulo Martins
Integrator
Benedetto Gallese
Integrator
Yong Kian Sin IEC61508 engineer
François Bellorini
Integrator
David Brodrick
Integrator
Jeong Han Lee Integrator
Consultants
Julen Etxeberria
Junior controls engineer
Szandra Kövecses
Lead integrator
Krisztián Löki
Integrator
Thilo Friedrich Systems Engineer
Karin Rathsman Senior scientist
Fredrik Luthander
Software engineer
Wojtek Fabianowski
in-kind manager
Jan-Åke Persson
Senior software engineer
Tomasz Brys
Integrator
Controls infrastructure
Remy Mudingay
Susann Skarin Sys Admin
Alessio Curri ICS administrator
Viktor Fred
Electrical engineer
Benjamin Bertrand
Software engineer
Angel Monera
FPGA Engineer
Anni Frönell
PMO
John Sparger
Integrator
Stephane Gabourin MPS engineer
William Ledda
Integrator
Miklós Boros
Target Integrator
Nour Akel
Installation cordinator
Enric Bargalló
Lead Analyst
Manorma Kumar
PSS analysis
Simone Farina Embedded systems engineer
Mehdi
Mohammednezhad
Michael Davidsaver
Expert EPICS
Oliver Talevski
Embedded engineer
David Sánchez Valde-
peñas Automation Engineer
Fredrik Söderberg
Software engineer
Mattias Eriksson
MPS Technician
Faye Chicken
Controls Technician
Peter Holgersson
Electrical Engineer
Peter van Velze
Controls Technician
Anders Harrisson
Software Engineer
Hardware & Integration
Henrik Carling
Johan Christensson
Network Engineer
Thomas Fay Integrator
Saeed Haghtalab
Controls Engineer
Begin 2018-01-08
Banafsheh Hajinasabi
Software engineer
Georg Weiss
Software engineer
Begin 2017-12

## Slide 9: Deliverables by partners
Deliverables by ICS/IPNO
Establish the elliptical cryogenic control system specifications based on instruments/sensors and control devices integrated in the elliptical cryomodules and valve boxes, but also regarding the interface requirement to the ESS main control system.
Perform the detailed design of the control system, in particular the rack integration and the cable routing of the whole system.
Program the PLCs to integrate the cryogenic sequences as they are defined by the cryomodule and valve box designers.
Support to ESS for the study of the system physical implementation in the klystron gallery and in the linac tunnel.
Deliverables by ACCSYS-WP10/ACCSYS-WP05/CEA
Instrument list of the elliptical cryomodule
Operation modes and cryogenic sequences of the elliptical cryomodule
Deliverables by ACCSYS-WP11/WUT
Instrument list of the elliptical valve box
Operation modes and cryogenic sequences of the elliptical valve box

## Slide 10: Time plan from ICS perspective
2017
2018
Today
Nov
Dec
2018
Feb
Mar
Apr
May
Jun
Jul
Aug
RF LPS Lab Prototype
2017-12-22
RF Cell Interlock Logic
2018-02-02
RF CS Hardware test start
2018-06-01
CDS CS Factory Acceptance Test (s7driver)
2018-03-16
CDS CS RFI
2018-04-27
CDS CS Site Acceptance Review (hardware test including vacuum) done
2018-08-31
PSS for TS2 analysis and preliminary documentation
2018-02-02
PSS for TS2 RFI (bunker ready for PSS)
2018-03-30
PSS for TS2 Installation complete
2018-04-20
PSS for TS2 Validation
2018-05-25
2017-11-06 -- 2017-12-22
RF Local Protection System
2018-01-08 -- 2018-02-02
RF Cell Interlock Design
2018-02-05 -- 2018-06-01
RF Control System
2017-11-23 -- 2018-03-16
CDS Control System (IPNO, FR)
2018-03-12 -- 2018-07-12
Control System Infrastructure installations
2018-02-05 -- 2018-03-30
PSS for TS2 Hardware and Software design

## Slide 11: Areas of further attention ?
LLRF
Modulators
Water cooling systems
Auxiliary systems

## Slide 12: Some pictures from site…

## Slide 13: Racks

## Slide 14: Questions?
Thank You!