## Slide 1
TG3 Process /Part 2
Gábor László
NSS Lead Instrument Engineer
13.02.2018

## Slide 2: TG3 Description documents
(By Peter Sångberg & Gábor Lászlo)

## Slide 3: ESS Contribution

## Slide 4: Scope of NSS TG3 Review
Basic scope
Verification of the structure of the design proces and completeness of the documentation (not content verification!)
Verification of compliance with ESS standards
Verification of instrument integration /Spatial, infrastructural, logistics, schedule/
In case of a Stage also the verification of the completeness of the internal interface definition.
Additional scope of the Technology Groups are defined individually by them, considering the available time, resources and legal(SSM) requirements.

## Slide 5: Technology group specific TG3 scope definition (NSS)
Motion control
The details of the necessary planning and technical requirements can be found here: ESS-0240219
Chopper Team
The details of the necessary planning and technical requirements can be found here: ESS-0239466
Template for tendering: ESS-0178215
Sample Evironment (SAD Team)
The details of the necessary planning and technical requirements can be found here: ESS-0189147
NOSG:
The shielding requirements can be found here: ESS-0052625
There are QA requirements are in the handbook: ESS-0039408

## Slide 6: Technology group specific TG3 scope
Cooling
3D Envelope of the out of bunker cooling system according to the P&ID from cooling Group
Vacuum
3D Envelope of the out of bunker cooling system according to the P&ID from Vacuum Group
ICS
No specific requirement
PSS
PSS hazard identification document: ESS-0135291
Detector Team: No specified requirements yet
DMSC: No specified requirements yet

## Slide 7: Phase 2 Communication with Technology groups
Detector
DMSC
Chopper
ES&H
ESS Rad. Safety
MCA
SAD
NOSG
ICS
PSS
Cooling
Vacuum
INSTRUMENT
TEAM
DETAILED DESIGN
Cooling P&ID
PSS DE
ICS PE incl. FBS structure
COMSOL Simulation
Table of motion
Control details
Control details
Input for FBS
Control details
Table of motion
Control details
Control details

## Slide 8: Phase 2 Communication with Technology groups
Detector
DMSC
Chopper
ES&H
MCA
SAD
NOSG
ICS/MPS
PSS
Cooling
Vacuum
INSTRUMENT
TEAM
ESS-0052625, ESS-0039408
ESS-0189147
ESS-0047810, ESS-0100583
Survey
Table of Motion
Vacuum Chamber Data
Size and placement of comp.
Size and placement of comp.
Vacuum P&ID
Cooling P&ID
3D Vacuum Envelope (OOB)
3D Cooling Envelope (OOB)
Preliminary Vacuum Design
Standards/ Guidelines
https://confluence.esss.lu.se/display/SPD/Instrument+Projects
COMSOL Simulation
S.E. Suite List
Detector List
Chopper Registry
Prel.Vacuum Design
Prel.Cooling Design
Chopper Design
Motion C. Design
More Items With Cooling
Neutron Optics Design,
Shielding Analysis,
Detector Design,
Sample Environment
Clarifying Functional Breakdown
Preliminary FBS
Preliminary ICS Integration
Risk analysis
Potential Risk Mitigation
Potential Risk Mitigation
Potential Risk Mitigation
Potential Risk Mitigation
Potential Risk Mitigation
Potential Risk Mitigation
Answers to PSS questionaire
Potential Risk Mitigation
Preliminary PSS Design
Prel. PSS and MPS Design
Prel. ICS Design
Preliminary MPS Design
TG3
Documents
ESS-0240219
ESS-0178215, ESS-0239466
TG3 requirements

## Slide 9: Summary Tables
Motion control:
Repository: https://confluence.esss.lu.se/display/MCAG/Instruments

## Slide 10: Summary Tables
Chopper registry
Repository: https://confluence.esss.lu.se/display/CG/Neutron+chopper+registry+@+ESS

## Slide 11: Summary Tables
Sample Environment Suite List
Repository: https://1drv.ms/x/s%21AuCQb_HPf3b9g8g2HHqvybpQKix-Lg

## Slide 12: Staged Phase 2 Process Example
Phase 2
Phase 2/2 (TG3-2)
In bunker components
Phase 2/1
(In monolith optics)
(Final TG3)
Phase 2/n
(TG3-n-1)
Phase 2/n-1
TG3-1
TG3-2
TG3-n-1
Final TG3

## Slide 13: Review Process

## Slide 14: Typical Example (For the first 8 instruments)
Stage 0
    Procurement of NBOA
Stage 1
  Early procurement of Choppers
Stage 2
  Early procurement of remaining Bunker components
Stage 3
  Early procurement of the detector vessel
Stage 4
  Design of the entire remaining system

## Slide 15: Stage 1. Early procurement of Choppers
Tendering (First phase of Stage 1)
Deliverables before call for tender (Assuming no changes since TG2):
Optical analysis data (Unless it was delivered during Phase 1)
Call for tender /Technical parts shall be in english/ (Template: ESS-0178215)
Schedule
Declaration of conformity with Appendix 1
ESS action:
Approval for Schedule and Resources
Chopper team shall Review the call for thender based on ESS-0178215
Review meeting is necessary since no Sub TG3 is required after the detailed engineering. Major part of approval of the sub TG3 is the approval of the CFT.
NSS Response time: less than 2 weeks

## Slide 16
APPENDIX 1
/Procurement verification/
There has to be a CDR between the Instrument team and the supplier.
(For the approval of the CDR, ESS shall approve the design.)
Scope of the work / Expected execution of the specified product or service /
Performance requirements /Acceptable products or acceptable substitutions/
List of required submittals including documents list, language requirement
Request of a Quality-assurance plan from the supplier in the tender documentation
List of applicable codes and standards
The product has to be designed and manufactured according to ESS and European standards.
Details about the verification process (SAT, FAT), the delivery and the handover of the product/service
The Contract/Tender shall contain the following points
Sub TG3
If the NSS requirements are not compatible with the rules of the partner institute, or instruments schedule or the resource plan is conflicting with NSS planning then the issue has to be discussed and addressed by a common agreement.

## Slide 17: Stage 1. Early procurement of Choppers
Before CDR with subcontractor (Second phase of Stage 1)
UpdateTG2 WPS, Schedule, PBS, Budget
Project Quality Plan (General example provided)
Instrument Hazard Analysis complementing the Chopper Hazard Analysis /Provided by the Chopper Team/ if necessary
Radiation Safety Analysis complementing the Chopper Radiation Analysis /Provided by the Chopper Team/ if necessary
Sub-System Design Description (SSDD) Based on chopper team´s guidelines
  Units decription an validation against requirements
  Description of mechanical and infrastructural interfaces of the choppers
  Potential Chopper section of the PSS documentation
Assembly drawings with BOM identifying the quality, mass and distance range from the beam.
Reviewers: Chopper team, NSS Lead eng., Vacuum team, Cooling team, Survey, Remote handling, Spatial integration, NOSG, PSS (TBD), ES&H (Helena)
(Review meeting with the instrument team is necessary if there is a request for it)

## Slide 18: Stage 2. In-bunker components
Tendering (First phase of Stage 2)
Deliverables (Assuming no changes since TG2):
Before tender
Call for tender /Technical parts shall be in english/ (No template for the first)
Schedule
Declaration of conformity with Appendix 1
Reviewers (Only critical from schedulig perpective):
Planners, NSS Lead eng., NOSG, MCG (potential)
(Review meeting is not necessary unless there is a serious issue!)
NSS Response time: less than 1 week

## Slide 19: Stage 2. In-bunker components
Before CDR with subcontractor (Second phase of Stage 2)
UpdateTG2 WPS, Schedule, PBS, Budget
Project Quality Plan (General example provided)
In-Bunker part of the Instrument Hazard Analysis (Templates: ESS-0135291, ESS-0047810) (Customization)
In-Bunker part of the Radiation Safety Analysis (Template: ESS-0052625, ESS-0100307) (Customization)
Sub-System Design Description (SSDD)
    Units decription an validation against requirements
  Description of mechanical and infrastructural interfaces
  Potential PSS documentation
Assembly drawings with BOM identifying the quality, mass and distance range from the beam.
3D model + Assembly drawings
Reviewers: NSS Lead eng., Vacuum team, Survey, Remote handling, Spatial integration, NOSG, Bunker team (bunker operations), Survey, PSS (TBD), ESS Radiation Safety (TBD), ES&H (Helena)
Review meeting shall be scheduled. Furter scope of the meeting: PSS and ICS integration

## Slide 20: Stage 3. Detector Vessel
Tendering (First phase of Stage 3)
Deliverables (Assuming no changes since TG2):
Before tender
Call for tender /Technical parts shall be in english/ (No template for the first)
Schedule
Declaration of conformity with Appendix 1
Reviewers (Only critical from schedulig perpective):
Planners, NSS Lead eng., Detector team, Sample environment
(Review meeting is not necessary unless there is a serious issue!)

## Slide 21: Stage 3. Detector Vessel
Before CDR with subcontractor (Second phase of Stage 3)
UpdateTG2 WPS, Schedule, PBS, Budget
Project Quality Plan (General example provided)
Detector part of the Instrument Hazard Analysis (Templates: ESS-0135291, ESS-0047810) (Customization)
Detector part of the Radiation Safety Analysis (Template: ESS-0052625, ESS-0100307) (Customization)
Sub-System Design Description (SSDD)
  Units decription an validation against requirements
  Description of mechanical and infrastructural interfaces
  Potential PSS documentation
Assembly drawings with BOM identifying the quality, mass and distance range from the beam.
3D model + Assembly drawings
Reviewers: NSS Lead eng., Vacuum team, Detector team, SAD, ES&H(Helena)
Review meeting shall be scheduled. Furter scope of the meeting: PSS and ICS integration

## Slide 22: Stage 4. Entire remaining system
Tendering (First phase of Stage 4)
Deliverables (Assuming no changes since TG2):
Before tender
Call for tender /Technical parts shall be in english/ (No template for the first)
Schedule
Declaration of conformity with Appendix 1
Reviewers (Only critical from schedulig perpective):
Planners, NSS Lead eng., Detector team, Sample environment, NOSG, MCAG
(Review meeting is not necessary unless there is a serious issue!)

## Slide 23: Stage 4. Entire remaining system
Before CDR with subcontractor (Second phase of Stage 4)
UpdateTG2 WPS, Schedule, PBS, Budget
Project Quality Plan (General example provided)
Instrument Hazard Analysis (Templates: ESS-0135291, ESS-0047810) (Customization)
Radiation Safety Analysis (Template: ESS-0052625, ESS-0100307) (Customization)
Sub-System Design Description (SSDD)
  Units decription an validation against requirements
  Description of mechanical and infrastructural interfaces
System Design Description (SDD)
    Preliminary design for the internal utilities
    Complete PSS evaluation and design
    Description of mechanical and infrastructural interfaces for the whole system
    Integration: Interfaces: spatial/infrastructural/logistics, Data Aquisition, S.E. Operation
  System Integration and Verification Plan
  Preliminary plan for cold and hot commissioning
  Draft of System Operations & Maintenance Manual
Assembly drawings with BOM identifying the quality, mass and distance range from the beam.
Native 3D model + Assembly drawings

## Slide 24: Stage 4. Entire remaining system
Reviewers: NSS Lead eng., Vacuum team, Detector team, Sample Enviroment, MCAG, NOSG, ICS, PSS, ESS ES&H, NOSG, ESS Radiation Safety, SAD, Cooling, DMSC, Survey, R. handling, Waste management

## Slide 25: Questions?

## Slide 26
Thank You!

## Slide 27
Project Documentation
      Update of the Work Package Specification (WPS) Schedule, PBS, Budget etc. if applicable.
      Project Quality Plan (PQP)
It shall include identification of standards and procedures applied in design, procurement, manufacture and assembly, and planning for compliance testing and inspection.

## Slide 28
Safety Documentation
Instrument Hazard Analysis
  References:
  ESS-0047810 /ESS Guideline for Instrument Hazard Analysis/
  ESS-0100583 /Template for Instrument Hazard Analysis/
  ESS-0016468 / ESS rule for identification and classification of safety important components/
Radiation Safety Analysis
  References (Not exclusive):
  ESS-0052625 /NOSG phase 2 guidelines for designing instrument shielding for radiation safety/
  ESS-0100307 /NMX Cave shielding: H1 and H2 scenarios/

## Slide 29
System Documentation
System Requirements Specification update
  Update of the Phase 1 document, if necessary.
Sub-System Design Description (SSDD)
  List of characteristic sub-system properties and solutions derived from requirements, with references to the requirements in the System Requirement Specification (SRS).
  Low level Component(s) or unit(s) description with critical technical parameters and requirements /E.g.: RH compatibility, temperature stability, accuracy, range, load capacity( of Structural components, Bearings, Pressure systems, Lifting features), The compliance to requirements shall be indicated, with references, if applicable.
  The components that are detailed in the technology documents should be not detailed again, but has to be included. (Appendix 2./ next slide)

## Slide 30
Sub-System Design Description (SSDD) 2.

## Slide 31
Sub-System Design Description (SSDD) 2.
Integration Data:
  External interfaces of the instrument sub-system
  System- Sub-System internal interfaces
This information can be written or visual (2D drawings, 3D model views etc. with dimensions) and/or reference to such.
PSS Check-list
Design considerations, as applicable, to record the justification of the selection of a particular design solution in case there are several obvious alternatives. Selection criteria could be any combination of, but may not be limited to, the following aspects; maintenance, operations, remote handling, decommissioning, installation, cost-efficiency .
Sub-system 1.
Sub-system 2.

## Slide 32
Final TG3/
System Documentation
System Design Description (SDD)
References to the SSDDs.
Integration data:
  External interfaces to the Instrument. Shall include infrastructural interfaces and visual information on allocated footprint for the Instrument and the utilised area within this footprint - thus verifying the geometry. This information shall display that the instrument is not interfering with the local environment, the requested free path is available and there are no logistic issues around it.
  System design for integration to Data acquisition and analysis systems
  Operational analysis of integration to Sample Environment Equipment and Laboratory Infrastructure and logistics
This information can be written or visual (2D drawings, 3D model views etc. with dimensions) and/or reference to such.

## Slide 33
Preliminary design for the following cross system sub-systems (utilities), with references to the requirements in the System Requirements Specification:
  /Only include in the SDD if not entirely covered in the sub-systems/
  Power distribution
  Control system
  Personnel Safety System, PSS
  Cooling and other fluid systems
  Vacuum and gas support systems
Certificate of Conformity for Hazardous Materials and Sustainability [ISS]; - Specify exceptions to the list stipulating what materials not to use. Could be a separate attachment.
System Design Description (SDD)

## Slide 34
System Documentation
      System Integration and Verification Plan
Describes the activities and resources (heavy equipment, special tools, staff etc.) required for installation, integration and verification of the technical requirements and the schedule for these. These activities shall be described in accordance to ESS-0115143, NSS project schedule guideline.
      System Validation Plan,
Preliminary plan for cold and hot commissioning
Defining content and depth of detail of all activities to validate the realized product against the high level scientific requirements (CONOPS).
      Draft of System Operations & Maintenance Manual
The document is to be started early in the design work and is intended to evolve throughout the phase and into the coming phases as the design gradually matures.

## Slide 35
Detailed Technical Design
3D model
Detailed Drawing documentation

## Slide 36: CHESS

## Slide 37
Thank You!

## Slide 38
Brief Explanation of ESS Activities
Phase 2: Outsourced Design
Preliminary engineering, or design change
Phase 1
Definition of base parameters and requirements
Manufacturing
Detailed engineering
TG2
Procurement verification
Design review by ESS technology group
Sub TG3
Procurement verification (reply: 1 week)
Deliverables:
The technical part of tender
Schedule
Declaration of conformity with Appendix 1
ESS action:
Approval for Schedule and Resources
Comment the content (optional)
No personal meeting is necessary unless the NSS integration group recommends it.
Interim Review (if necessary)
Deliverables:
New technical information
ESS action:
Verification of Integration
Verification of change
Informal meeting. Either personal or via Vidyo/Skype
Sub TG3 (2 weeks)*
See below
Formal meeting with the involved ESS group(s)
/*: See ESS-0099059 for the detailed description of the deliverables/
Tendering

## Slide 39
Outsourced ESS Instrument Design Process of a Stage /Scenario 2
Outsourced Design
Preliminary engineering, or design change
Phase 1
Definition of base parameters and requirements
Manufacturing
Detailed engineering
TG2
Procurement verification
Sub TG3
ESS - Instrument
action:
Design review by ESS technology group
Example: NMX Sample environment robots
(Before CDR)
Tendering
Potential Checkpoint

## Slide 40
Outsourced ESS Instrument Design Process of a Stage /Scenario 3
Outsourced Design
Phase 1
Definition of base
parameters and
requirements
Preliminary engineering
Manufacturing
Detailed engineering
TG2
Sub TG3
Procurement verification
ESS - Instrument
action:
Example: NMX Chopper procurement
(Before CDR)
Tendering

## Slide 41
Outsourced ESS Instrument Design Process of a Stage /Scenario 1
Phase 2: Outsourced Design
Preliminary engineering, or design change
Phase 1
Definition of base parameters and requirements
Manufacturing
Detailed engineering
PDR
Tendering /contracting
CDR
Instrument -
Subcontractor activity:
Example: NMX Guide Procurement
TG2
Procurement verification
Design review by ESS technology group
Sub TG3
ESS - Instrument
action:
(Before CDR)
/*: See ESS-0099059 for the detailed descriptions of the deliverables/
Tendering