## Slide 1: CDR - PSS0 Installation and Commissioning Plan
Author Team Supervisor
A. Toral M. Eriksson S.L. Birch
M. Mansouri

## Slide 2: Introduction:
What is the objective of the PSS0 Installation & Commissioning Plan?
- To give an overview about the installation process and commissioning activities including milestones
Who are the stakeholders involved in the Installation & Commissioning Plan?
- Accelerator Division
- ICS Division
- Processkontroll AB

## Slide 3: PSS0 Installation and Commissioning Plan
2018
7
8
9
10
11
12
13
14
HV Fence Installed
Feb 12
Racks Delivered
Feb 22
System ready for Software deployment
Mar 20
System operational
Apr 7
Configuration before test
Mar 6
Feb 13
Feb 21
Field devices installation
Feb 15
Feb 16
FAT for racks
Feb 23
Feb 26
Installation of racks
Feb 26
Mar 5
Cable installation and termination
Mar 2
Mar 5
Main power to racks
Mar 7
Mar 9
Loop check
Mar 7
Mar 20
Software Development
Mar 20
Mar 22
HW and SW Integration
Mar 22
Mar 26
SAT
Mar 26
Mar 29
FIT
Mar 26
Apr 5
Validation
Apr 6
Handover
2018
Processkontroll
ICS

## Slide 4
Thank you for your attention,
any questions?