## Sheet1
Responses to Recommendations from the 16th t-TAC Meeting
Topic | TAC Recommendation | Target Project Response to TAC Recommendation
Bunker | tTAC comments: (1) - The bunker likely requires a compromise between reducing requirements and increasing budget. A budget increase is likely necessary, and some changes in access control may enable cost reductions. We encourage you to proceed along both paths ASAP. (2) - On the basis of the models presented the Committee was concerned about shielding gaps between the bunker and target station and potential streaming paths in the bunker wall and roof shielding. The committee recommends that theses aspects of the bunker shielding are reviewed. (3) - Special care should be given to minimize the activation of inserts and bunker components as this inherits significant future cost. (4) - If final design is done by external company that builds the bunker (design build), engineering oversight must be constant. (5) - Working arrangements for control of the spread of contamination from the bunker are required. (6) - The committee believes it to be essential that remote handling equipment to be used in the bunker is commissioned before activity levels in the bunker rise to a level restricting personnel access. This may make it necessary to limit the speed at which the accelerator commissioning can progress. (7) - The hazard in the bunker of life threatening dose rates (15kSv/h) has serious implications for the design of the personnel safety system to be used to control access to the bunker and neutron beam inserts. In particular the requirements for the control of the light shutters are complex and need urgent definition . Dose rate from neutron beam equipment shining through the open bunker roof may well be high enough to restrict access. tTAC recommendation: (8) Rec.1. Focused effort on the bunker should be a priority. | (1) Yes, agree. Measurements taken for example feasablity stude made to replace steel and HDP by heavy concrete. (2) The gaps have been rechecked and there are no shielding gaps in terms of streaming. (3) Agree, special attention is made to choose materials that gets as low activation as possible where applicable. (4) Yes, the plan is to have someone from ESS going to the supplier and supervise the engineering and manufacturing. (5) Agree, this is developped together with PSS and ESH. (6) Agree, this will be considered in the planing of the testing phase. (7) PSS is involved in the design of the light shutters. Once beam on target, access will be restricted and thereafter everything will be remote handled. (8) Agree, it has been made a priority. For example the Neutronics team has worked with Bunker as their main priority since autumn.
Beamlines | tTAC comments: (9) - For the NSS the integration process has to be improved as nearly all of the 15 instruments are progressing quickly in the detailed design phase. General questions raised by individual instruments as well as mutually formulated questions raised at ICON meetings have not been resolved in due time. Coordination with the instruments will have no impact after their detailed design phase is completed. (10) - Installation of beamlines in an unfinished building will required erection of temporary enclosures and other measures to protect the equipment to be installed. This will delay completion of the building which should be accounted for in the analysis of installation options. tTAC recommendation: (11) Rec.2. Installing beamlines in an unfinished building is a difficult and risky task. Consider options to avoid this. (12) Rec.3. Take account of the beamline settlement over time to maintain precise alignment which influences instrument performance. | (9) Agree, hence NSS has a CORE Engineering team helping instruments to align their design to ESS requirements. (10) We are planning the buildings to be finished enough when installation starts, hence no delays for this reason are foreseen. For example according to plan when part of the building is ready it will be sealed by temporary walls and instrument installation can start. (11) NSS is working to minimize those risks. Is has also been considered in the NSS inputs for the project rebaseline. (12) It's part of the considerations from Detailed Design from every instrument and Survey and Alignement Group. Calculations as well as practical load tests where possible are beeing made on slab settlement.
Neutron Beam Port Inserts | tTAC comments: (13) - Installing the NBPI with the building not finished (and thus “dirty”) poses a risk of having to deal with higher levels of contamination later. (14) - What if something goes wrong during remote handling? Do you have backup plans? (15) - During a change out, all shutters must be locked but the one where the NBPI is to be exchanged needs to be moved. Moving the wrong shutter could be lethal to operation staff. (16) - The committee recommends that the design of the PSS interlock system for this area be undertaken as a matter of urgency as this could well effect the detailed design of the neutron beam insert handling equipment. | (13) Agree, measurements have to be made in order to minimize the "dirt" and will be planned for installation phase. -Building D01&D03 shall be made weather tight prior to installation. -Tents will be used when installing the NBPIs. (14) Right, backup plans have to made in order to minimize the risk. Dry runs/training sessions wil be performed before beam on target. (15) Right, detailed instructions shall be elaborated as well as making a fail-safe design to the extent that is possible. (16) Agree.
Integration reviews | tTAC comments: (17) - As with any new procedure it will take time for the advantages of the Integration review to become clear. The example presented was ambitious in scope and the presence of the TAC members may well have inhibited the free flow of discussion amongst the project staff. Nonetheless, the committee felt that useful progress was made and some interface issues needing action were identified as well as some useful technical comments. (18) - The committee recommends the project to continue with this initiative and review the impact of integration reviews when more experience has been gained. (19) - The scale of the reviews should match the risk associated with the component and design. A ‘light touch’ would be sufficient in many cases. | (17) Ok, thanks. (18) Yes, it will be considered to be made. (19) Ok, we will consider this for future reviews.
General | tTAC comments: (20) - Systematic documentation efforts are good and needed . However, in view of the need to reduce staff, tasks like “having all as-built drawings in 3D CAD” could be slowed down and the resources used for design and installation work instead. Focus should be limited to items required in the short term and those for which the input will not be available later. (21) - It should be required that ESS staff and partners provide an appropriate level of documentation for archiving. (22) - Photography of equipment as a record of installation should be made mandatory at least for all parts where future access is restricted or not possible (e.g., Target station). (23) - Communication is important: with in-kind partners, vendors, within the project, etc. (24) - Procedures in the engineering handbook are good and are sorted by phases. Maybe “decommissioning” should be added as a phase to remind staff of issues such as waste handling during design | The first issue of ESS-0092276 "ESS Handbook for Engineering Management" was released on January 2, 2018. This handbook specifies the deliveries, in terms of documentation and archive material, that are required after each phase of an engineering work element. It is certainly acknowledged that prioritization is needed in order to use limited staff resources wisely, and such assessment is done regularly with focus on design and installation works while at the same time not slip too much on the follow-up on essential as-built documentation. The engineering handbook does not yet include a description of the decommissioning of a system. However, it is mentioned as a possible addition for future revision of this document.