## Slide 1: Installation Testing and Commissioning Planning
Ciprian Plostinar,
On behalf of the ESS AD Installation and Planning Teams
TAC#17
www.europeanspallationsource.se
12 April 2018

## Slide 2: Key Assumptions
Installation
In-Kind Model
Testing
Commissioning
Ready for Installation Dates:
Some contractual
Optimised Sequence:
Logic
Safety
Flexibility
Parallel Installation and Commissioning:
Shielding Wall
Others “best estimate”
Safety Measures
Correct Gateways
Suitable Reviews
Realistic time allocation
Relevant Permits
SSM
Hardware
Beam
Key Dependencies
Critical Parameters
Other Divisions
Coordinated Installation of Utilities/Services
Demanding Schedule
No Internal Float

## Slide 3: Installation Example – Sequence
RF Cell Installation Sequence | 1. Empty Cell | 2. Cable Trays | 3. Racks
4. Cable Trays Racks | 5. RFDS on Wall | 6. RFDS Supports | 7. Cooling Install
8. Loads, Circ., Etc, | 9. Cable Trays to RF | 10. Klystrons | 11. Modulators

## Slide 4: Testing Example – Engineering Process

## Slide 5: Commissioning Example – Planning Check

## Slide 6: ISrc and LEBT
First major accelerator installation milestone at ESS
Main installation priority for early 2018
Major effort on installation of utilities in the tunnel and the FEB
  This allowed the ISrc and LEBT assembly to proceed as planned (January 2018).
Current focus:
  Cable pulling, cable terminations, rack filling and testing, ISrc HV safety cage, etc.
  Energising and SSM Permits
Current planning forecast:
  Safety Readiness Review: June 2018.
  First Beam: July 2018

## Slide 7: ISrc and LEBT Detailed Timeline
2017
2018
Sep
Oct
Nov
Dec
2018
Feb
Mar
Apr
May
Jun
Jul
Installation Readiness Review
Sep 15
Delivery to ESS
Dec 12
ISrc and LEBT Assembly Begins at ESS
Jan 16
Assembly
Completed
Feb 16
Energising Permit
Mar 5
SSM Permit
May 28
Start of Beam
Commissioning
Jul 9
Sep 18 - Nov 3
Final Tests in Catania
Nov 6 - Nov 30
ISrc and LEBT Disassembly
Dec 1 - Dec 12
Transport to Lund
Dec 13 - Dec 22
Delivery Acceptance Tests
Jan 16 - Feb 16
ISrc and LEBT Assembly
Apr 9 - Apr 13
HV Safety Cage Installation by ESS
Apr 16 - May 11
PSS0 Installation
May 14 - May 25
PSS0 Validation
May 28 - Jun 22
Hardware Tests
Jun 25 - Jul 6
SRR1
Oct 16 - Dec 22
Utilities Installation - ISrc+LEBT Area
Jan 8 - May 25
Utilities Installation, Cable Pulling and Terminations, Etc. - FEB
Oct 16 - Dec 22
ICS Installation
Jan 8 - May 25
ICS Installation

## Slide 8: Key Deliveries: ISrc and LEBT
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Proposed Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
Ion Source | 06-Nov-17 | 03-Jan-18 | 15-Jan-18 | 168 | 12 | Low | 
LEBT | 06-Nov-17 | 03-Jan-18 | 15-Jan-18 | 168 | 12 | Low | 
RFI Date
Installation Date
Critical Path Date
Delivery Float
Installation Float

## Slide 9: NC Linac
Major milestones:
  RFQ RFI: September 2018
  MEBT RFI: February 2019
    SSPA for buncher 1: April 2019
    SSPA for bunchers 2,3: August 2019
    Power Converters for MEBT Magnets: July 2019.
  DTL4 RFI: January 2019
  DTL1 RFI: March 2019
  DTL3 RFI: April 2019
  DTL2 RFI: June 2019
  DTL5 RFI: October 2019
RF System Status:
  Delays reported throughout 2017 due to unforeseen funding issues at ESS Bilbao
    These have now been resolved
  Some procurement difficulties, but progress has been made
  Many tenders remain to be placed (uncertainty), but better confidence on delivery dates
  ESS has started the process of procuring critical spares (loads/circulators) -> risk control.
  Important driver for the NC Linac commissioning plan
Shield wall between DTL4 and the Spoke section allows installation to continue in the cold linac while beam commissioning the NC linac.
  This is possible by postponing DTL 5 installation
  Important schedule delay mitigation/flexibility/control

## Slide 10: NC Linac – Installation Timeline
Tunnel
Gallery
2018
2019
2020
2021
ISrc to LEBT
4/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
03/09/18 - 09/11/18
RFQ Installation
07/01/19 - 01/02/19
DTL4 Installation
04/02/19 - 01/03/19
MEBT Installation
11/03/19 - 05/04/19
DTL1 Installation
08/04/19 - 03/05/19
DTL3 Installation
10/06/19 - 05/07/19
DTL2 Installation
27/07/20 - 21/08/20
DTL5 Installation
11/02/19 - 22/02/19
RFQ Klystron
25/02/19 - 08/03/19
DTL1 Klystron
11/03/19 - 12/04/19
Modulator 1
11/03/19 - 03/05/19
Waveguides
06/05/19 - 12/07/19
Loads and Circulators
29/07/19 - 09/08/19
Modulator 2
12/08/19 - 23/08/19
Modulator 3
02/09/19 - 13/09/19
DTL2 Klystron
07/10/19 - 18/10/19
DTL3 Klystron
04/11/19 - 15/11/19
DTL4 Klystron
02/12/19 - 13/12/19
DTL5 Klystron

## Slide 11
2018
2021
Today
2018
2019
2020
2021
ISrc to LEBT
4/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
50 days
03/09/18 - 09/11/18
RFQ Installation
20 days
07/01/19 - 01/02/19
DTL4 Installation
20 days
04/02/19 - 01/03/19
MEBT Installation
20 days
11/03/19 - 05/04/19
DTL1 Installation
20 days
08/04/19 - 03/05/19
DTL3 Installation
20 days
10/06/19 - 05/07/19
DTL2 Installation
20 days
27/07/20 - 21/08/20
DTL5 Installation
80 days
17/12/18 - 05/04/19
Stubs Installation
20 days
17/12/18 - 11/01/19
RFDS Support Structure
10 days
14/01/19 - 25/01/19
Water Cooling for RF
5 days
28/01/19 - 01/02/19
Trays and Cables RF
5 days
04/02/19 - 08/02/19
Power to Modulators
10 days
11/02/19 - 22/02/19
RFQ Klystron
10 days
25/02/19 - 08/03/19
DTL1 Klystron
25 days
11/03/19 - 12/04/19
Modulator 1
40 days
11/03/19 - 03/05/19
Waveguides
50 days
06/05/19 - 12/07/19
Loads and Circulators
100 days
25/02/19 - 12/07/19
RF System Commissioning (RFQ and DTL1)
10 days
15/07/19 - 26/07/19
PSS1 Validation
60 days
29/07/19 - 18/10/19
RF Conditioning (RFQ and DTL1)
10 days
21/10/19 - 01/11/19
SRR2
65 days
04/11/19 - 31/01/20
Beam Commissioning (ISrc to DTL1)
10 days
29/07/19 - 09/08/19
Modulator 2
10 days
12/08/19 - 23/08/19
Modulator 3
10 days
02/09/19 - 13/09/19
DTL2 Klystron
10 days
07/10/19 - 18/10/19
DTL3 Klystron
10 days
04/11/19 - 15/11/19
DTL4 Klystron
10 days
02/12/19 - 13/12/19
DTL5 Klystron
95 days
23/09/19 - 31/01/20
Full NC RF System Commissioning
10 days
03/02/20 - 14/02/20
PSS1 Re-Validation
40 days
17/02/20 - 10/04/20
RF Conditioning (DTL2, 3, 4)
10 days
13/04/20 - 24/04/20
SRR3
65 days
27/04/20 - 24/07/20
Beam Commissioning (ISrc to DTL4)
Tunnel
Gallery
SRR/PSS/Commissioning/Conditioning
Stubs

## Slide 12: Key Deliveries: RFQ
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
RFQ | 09-Jul-19 | 03-Sep-18 | 03-Sep-18 | 245 | 0 | Med | 
RFQ Klystron | 05-Feb-18 | 01-Jul-18 | 11-Feb-19 | 0 | 225 | Low | 
Modulator 1 (RFQ, DTL1) | 24-Sep-18 | 14-Dec-18 | 11-Mar-19 | 0 | 84 | Low | 
RFQ Circ./Loads | 04-Feb-19 | 06-May-19 | 06-May-19 | 0 | 0 | High | 
RFQ RFDS | 07-Jan-19 | 04-Mar-19 | 04-Mar-19 | 0 | 0 | High | 
The RFQ does not affect the critical path of the re-baselined ACCSSYS installation plan, as this is driven by the NC Linac RF System Delays

## Slide 13: Key Deliveries: MEBT
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
MEBT | 01-Feb-19 | 01-Feb-19 | 04-Feb-19 | 112 | 3 | Med | 
B1 SSPA | 03-Apr-19 | 03-Apr-19 | 08-Apr-19 | 119 | 5 | Med | 
B2 SSPA | 12-Aug-19 | 12-Aug-19 | 12-Aug-19 | 0 | 0 | Med | 
B3 SSPA | 12-Aug-19 | 12-Aug-19 | 12-Aug-19 | 0 | 0 | Med | 
PC for MEBT Magnets | 04-Jul-19 | 04-Jul-19 | 08-Jul-19 | 35 | 4 | Med | 
Some delayed MEBT deliveries, do not affect the critical path of the re-baselined ACCSYS installation plan, as they are hidden by larger delays experienced in different parts of the project (i.e. NC Linac RF)

## Slide 14: Key Deliveries: DTL
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
DTL1 | 16-Nov-18 | 10-Feb-19 | 11-Mar-19 | 42 | 29 | Med | 
DTL2 | 30-Apr-19 | 05-Jun-19 | 10-Jun-19 | 7 | 5 | Med | 
DTL3 | 08-Mar-19 | 15-Mar-19 | 08-Apr-19 | 42 | 24 | Med | 
DTL4 | 18-Sep-18 | 01-Jan-19 | 07-Jan-19 | 77 | 6 | Low | 
DTL5 | 30-Sep-19 | 30-Sep-19 | 27-Jul-20 | 0 | 301 | Low | 
DTL 1 Klystron | 19-Feb-18 | 01-Jul-18 | 25-Feb-19 | 0 | 239 | Low | 
DTL 2 Klystron | 05-Mar-18 | 01-Jul-18 | 02-Sep-19 | 0 | 428 | Low | 
DTL 3 Klystron | 06-May-19 | 07-Oct-19 | 07-Oct-19 | 0 | 0 | Med | 
DTL 4 Klystron | 20-May-19 | 04-Nov-19 | 04-Nov-19 | 0 | 0 | Med | 
DTL 5 Klystron | 03-Jun-19 | 02-Dec-19 | 02-Dec-19 | 266 | 0 | Med | 

## Slide 15: Key Deliveries: DTL
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
Modulator 2 (DTL2, DTL3) | 25-Mar-19 | 14-Jun-2019 | 29-Jul-19 | 0 | 45 | Low | 
Modulator 3 (DTL4, DTL5) | 25-Mar-19 | 14-Jun-2019 | 12-Aug-19 | 0 | 59 | Low | 
NC Circ/Loads (Full System) | 04-Feb-19 | 31-May-19 | 03-Jun-19 | 0 | 3 | Med | 
NC RFDS (Full System) | 07-Jan-19 | 27-May-19 | 27-May-19 | 0 | 0 | Med | 

## Slide 16: SC Linac
Four major installations on critical path:
  Cryomodules
    13 SPK CMs, 9 MB CMs and 2 HB CMs to be installed initially
    The rest of the HB CMs to be installed after RBOT date.
    As of today, the earliest installation date of the first cryomodule is end of the 2019.
  Cryogenics Distribution System
    Cryomodule installation can only start after the complete CDS has been commissioned.
  Linac Warm Units
    LWUs will be installed after the cryomodule installation.
    HEBT LWU to be installed first
  RF Power Stations for Spokes
    Delivery and installation: July 2019 to August 2020

## Slide 17: SC Linac – Spoke Installation Timeline
Tunnel
Gallery
2018
2019
2020
2021
ISrc to LEBT
4/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
19/08/19 - 15/11/19
SPK CDS Installation
18/11/19 - 07/08/20
SPK CM Installation
22/06/20 - 25/09/20
SPK LWU Installation
08/01/18 - 23/02/18
SPK RFDS Support Structures
02/04/18 - 27/07/18
SPK Waveguides
16/04/18 - 10/08/18
SPK Loads and Circulators
12/08/19 - 25/09/20
SPK RF Power Stations

## Slide 18: Key Deliveries: Spoke Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
SPK-010CRM | 05-Nov-18 | 21-Jun-19 | 18-Nov-19 | 0 | 150 | Low | 
SPK-020CRM | 03-Dec-18 | 02-Aug-19 | 02-Dec-19 | 0 | 122 | Low | 
SPK-030CRM | 07-Jan-19 | 13-Sep-19 | 16-Dec-19 | 0 | 94 | Low | 
SPK-040CRM | 04-Feb-19 | 11-Oct-19 | 27-Jan-20 | 0 | 108 | Low | 
SPK-050CRM | 04-Mar-19 | 08-Nov-19 | 10-Feb-20 | 0 | 94 | Low | 
SPK-060CRM | 01-Apr-19 | 06-Dec-19 | 24-Feb-20 | 0 | 80 | Med | 
SPK-070CRM | 06-May-19 | 17-Jan-20 | 09-Mar-20 | 0 | 52 | High | 
SPK-080CRM | 03-Jun-19 | 14-Feb-20 | 23-Mar-20 | 0 | 38 | High | 
SPK-090CRM | 01-Jul-19 | 13-Mar-20 | 13-Apr-20 | 0 | 31 | High | 
SPK-100CRM | 05-Aug-19 | 14-Apr-20 | 11-May-20 | 0 | 27 | High | 
SPK-110CRM | 02-Sep-19 | 08-May-20 | 08-Jun-20 | 0 | 31 | High | 

## Slide 19: Key Deliveries: Spoke Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
SPK-120CRM | 07-Oct-19 | 05-Jun-20 | 08-Jun-20 | 0 | 3 | High | 
SPK-130CRM | 04-Nov-19 | 03-Jul-20 | 06-Jul-20 | 0 | 3 | High | 
SPK-010LWU | 16-Mar-20 | 16-Mar-20 | 24-Aug-20 | 0 | 161 | Low | 
SPK-020LWU | 16-Sep-19 | 16-Sep-19 | 16-Mar-20 | 0 | 182 | Low | 
SPK-030LWU | 16-Sep-19 | 16-Sep-19 | 16-Mar-20 | 0 | 182 | Low | 
SPK-040LWU | 28-Oct-19 | 28-Oct-19 | 16-Mar-20 | 0 | 140 | Low | 
SPK-050LWU | 28-Oct-19 | 28-Oct-19 | 30-Mar-20 | 0 | 154 | Low | 
SPK-060LWU | 28-Oct-19 | 28-Oct-19 | 30-Mar-20 | 0 | 154 | Low | 
SPK-070LWU | 03-Feb-20 | 03-Feb-20 | 30-Mar-20 | 0 | 56 | Med | 
SPK-080LWU | 16-Mar-20 | 16-Mar-20 | 13-Apr-20 | 0 | 28 | Med | 
SPK-090LWU | 28-Oct-19 | 28-Oct-19 | 13-Apr-20 | 0 | 168 | Low | 

## Slide 20: Key Deliveries: Spoke Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
SPK-100LWU | 28-Oct-19 | 28-Oct-19 | 13-Apr-20 | 0 | 168 | Low | 
SPK-110LWU | 28-Oct-19 | 28-Oct-19 | 27-Apr-20 | 0 | 182 | Low | 
SPK-120LWU | 09-Dec-19 | 09-Dec-19 | 27-Apr-20 | 0 | 140 | Low | 
SPK-130LWU | 16-Mar-20 | 16-Mar-20 | 27-Apr-20 | 0 | 42 | Med | 
Spokes CDS | 19-Aug-19 | 19-Aug-19 | 19-Aug-19 | 0 | 0 | Med | 
Spoke RF PS Batch 1 | 08-Jul-19 | 12-Aug-19 | 12-Aug-19 | 0 | 0 | Med | 
Spoke RF PS Batch 2-6 | 09-Sep-19 | 11-Oct-19 | 11-Oct-19 | 0 | 0 | Med | 
Spoke RF PS Batch 7-11 | 07-Jan-20 | 07-Jan-20 | 07-Jan-20 | 0 | 0 | Med | 

## Slide 21: Key Deliveries: Spoke Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
Spoke RF PS Batch 12-16 | 09-Mar-20 | 09-Mar-20 | 09-Mar-20 | 0 | 0 | Med | 
Spoke RF PS Batch 17-21 | 25-May-20 | 25-May-20 | 25-May-20 | 0 | 0 | Med | 
Spoke RF PS Batch 22-26 | 15-Jul-20 | 15-Jul-20 | 15-Jul-20 | 0 | 0 | Med | 

## Slide 22: SC Linac – MBL and HBL Installation Timeline
Tunnel
Gallery
2018
2019
2020
2021
ISrc to LEBT
4/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
03/12/18 - 15/11/19
Elliptical CDS Installation
18/11/19 - 01/06/20
MBL CM Installation
11/05/20 - 03/07/20
MBL LWU
01/06/20 - 07/08/20
HBL CM Installation
30/03/20 - 25/09/20
HBL LWU 1-10
05/08/19 - 13/12/19
HBL LWU 11-21
05/03/18 - 21/09/18
MBL/HBL RFDS Support Structures
30/07/18 - 06/09/19
MBL/HBL Waveguides
13/08/18 - 20/09/19
MBL/HBL Loads Circulators
13/08/18 - 27/09/19
MBL Klystrons
22/04/19 - 10/01/20
MBL Modulators

## Slide 23: Key Deliveries: Medium Beta Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
MBL-010CRM | 05-Aug-19 | 02-Sep-19 | 18-Nov-19 | 0 | 77 | Low | 
MBL-020CRM | 02-Sep-19 | 07-Oct-19 | 02-Dec-19 | 0 | 56 | Low | 
MBL-030CRM | 07-Oct-19 | 04-Nov-19 | 16-Dec-19 | 0 | 42 | Low | 
MBL-040CRM | 04-Nov-19 | 02-Dec-19 | 13-Jan-20 | 0 | 42 | Low | 
MBL-050CRM | 02-Dec-19 | 06-Jan-20 | 27-Jan-20 | 0 | 21 | Med | 
MBL-060CRM | 06-Jan-20 | 03-Feb-20 | 10-Feb-20 | 0 | 7 | Med | 
MBL-070CRM | 03-Feb-20 | 02-Mar-20 | 02-Mar-20 | 0 | 0 | Med | 
MBL-080CRM | 02-Mar-20 | 06-Apr-20 | 06-Apr-20 | 0 | 0 | Med | 
MBL-090CRM | 06-Apr-20 | 04-May-20 | 04-May-20 | 0 | 0 | Med | 
MBL-010LWU | 09-Dec-19 | 09-Dec-19 | 11-May-20 | 0 | 154 | Low | 
MBL-020LWU | 03-Feb-20 | 03-Feb-20 | 11-May-20 | 0 | 98 | Low | 

## Slide 24: Key Deliveries: Medium Beta Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
MBL-030LWU | 03-Feb-20 | 03-Feb-20 | 11-May-20 | 0 | 98 | Low | 
MBL-040LWU | 09-Dec-19 | 09-Dec-19 | 25-May-20 | 0 | 168 | Low | 
MBL-050LWU | 09-Dec-19 | 09-Dec-19 | 25-May-20 | 0 | 168 | Low | 
MBL-060LWU | 09-Dec-19 | 09-Dec-19 | 25-May-20 | 0 | 168 | Low | 
MBL-070LWU | 03-Feb-20 | 03-Feb-20 | 08-Jun-20 | 0 | 126 | Low | 
MBL-080LWU | 16-Mar-20 | 16-Mar-20 | 08-Jun-20 | 0 | 84 | Low | 
MBL-090LWU | 16-Mar-20 | 16-Mar-20 | 08-Jun-20 | 0 | 84 | Low | 
Elliptical CDS | 03-Dec-18 | 03-Dec-18 | 03-Dec-18 | 0 | 0 | Med | 

## Slide 25: Key Deliveries: Medium Beta Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
MBL Klystrons 1 | 16-Jul-18 | 19-Jul-18 | 13-Aug-18 | 392 | 25 | Low | 
MBL Klystrons 2 | 16-Jul-18 | 17-Aug-18 | 27-Aug-18 | 392 | 10 | Low | 
MBL Klystrons 3 | 16-Jul-18 | 31-Aug-18 | 24-Sep-18 | 378 | 24 | Low | 
MBL Klystrons 4 | 16-Jul-18 | 19-Sep-18 | 08-Oct-18 | 378 | 19 | Low | 
MBL Klystrons 5 | 13-Aug-18 | 16-Oct-18 | 22-Oct-18 | 378 | 6 | Low | 
MBL Klystrons 6 | 13-Aug-18 | 26-Oct-18 | 29-Oct-18 | 378 | 3 | Low | 
MBL Klystrons 7 | 13-Aug-18 | 20-Nov-18 | 26-Nov-18 | 371 | 6 | Low | 
MBL Klystrons 8 | 13-Aug-18 | 30-Nov-18 | 10-Dec-18 | 371 | 10 | Low | 
MBL Klystrons 9 | 10-Sep-18 | 18-Dec-18 | 07-Jan-19 | 301 | 20 | Low | 

## Slide 26: Key Deliveries: Medium Beta Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
MBL Klystrons 10 | 10-Sep-18 | 15-Jan-19 | 21-Jan-19 | 301 | 6 | Low | 
MBL Klystrons 11 | 10-Sep-18 | 15-Mar-19 | 18-Mar-19 | 259 | 3 | Low | 
MBL Klystrons 12 | 10-Sep-18 | 29-Mar-19 | 01-Apr-19 | 259 | 3 | Low | 
MBL Klystrons 13 | 01-Oct-18 | 29-Apr-19 | 29-Apr-19 | 259 | 0 | Low | 
MBL Klystrons 14 | 01-Oct-18 | 21-May-19 | 27-May-19 | 245 | 6 | Low | 
MBL Klystrons 15 | 01-Oct-18 | 31-May-19 | 10-Jun-19 | 245 | 10 | Low | 
MBL Klystrons 16 | 01-Oct-18 | 26-Jun-19 | 01-Jul-19 | 238 | 5 | Low | 
MBL Klystrons 17 | 29-Oct-18 | 12-Jul-19 | 12-Jul-19 | 217 | 0 | Low | 
MBL Klystrons 18 | 29-Oct-18 | 20-Aug-19 | 26-Aug-19 | 196 | 6 | Low | 

## Slide 27: Key Deliveries: Medium Beta Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
MBL Klystrons 19 | 29-Oct-18 | 21-Aug-18 | 08-Oct-18 | 455 | 48 | Low | 
MBL Klystrons 20 | 29-Oct-18 | 13-Sep-18 | 22-Oct-18 | 455 | 39 | Low | 
MBL Klystrons 21 | 19-Nov-18 | 28-Sep-18 | 05-Nov-18 | 476 | 38 | Low | 
MBL Klystrons 22 | 19-Nov-18 | 26-Oct-18 | 19-Nov-18 | 476 | 24 | Low | 
MBL Klystrons 23 | 19-Nov-18 | 19-Nov-18 | 03-Dec-18 | 476 | 14 | Low | 
MBL Klystrons 24 | 19-Nov-18 | 19-Dec-18 | 07-Jan-19 | 462 | 19 | Low | 
MBL Klystrons 25 | 28-Jan-19 | 21-Dec-18 | 21-Jan-19 | 420 | 31 | Low | 
MBL Klystrons 26 | 28-Jan-19 | 24-Jan-19 | 04-Feb-19 | 420 | 11 | Low | 
MBL Klystrons 27 | 28-Jan-19 | 18-Feb-19 | 18-Feb-19 | 420 | 0 | Low | 

## Slide 28: Key Deliveries: Medium Beta Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
MBL Klystrons 28 | 28-Jan-19 | 08-Mar-19 | 11-Mar-19 | 413 | 3 | Low | 
MBL Klystrons 29 | 18-Feb-19 | 29-Mar-19 | 01-Apr-19 | 399 | 3 | Low | 
MBL Klystrons 30 | 18-Feb-19 | 29-Apr-19 | 29-Apr-19 | 385 | 0 | Low | 
MBL Klystrons 31 | 18-Feb-19 | 17-May-19 | 20-May-19 | 378 | 3 | Low | 
MBL Klystrons 32 | 18-Feb-19 | 11-Jun-19 | 17-Jun-19 | 364 | 6 | Low | 
MBL Klystrons 33 | 11-Mar-19 | 28-Jun-19 | 01-Jul-19 | 329 | 3 | Low | 
MBL Klystrons 34 | 11-Mar-19 | 12-Jul-19 | 15-Jul-19 | 329 | 3 | Low | 
MBL Klystrons 35 | 11-Mar-19 | 16-Aug-19 | 19-Aug-19 | 308 | 3 | Low | 
MBL Klystrons 36 | 11-Mar-19 | 06-Sep-19 | 09-Sep-19 | 301 | 3 | Low | 

## Slide 29: Key Deliveries: Medium Beta Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
MBL Mod 1 | 13-Aug-18 | 17-Apr-19 | 22-Apr-19 | 196 | 5 | Low | 
MBL Mod 2 | 07-Jan-19 | 12-Jun-19 | 17-Jun-19 | 196 | 5 | Low | 
MBL Mod 3 | 14-Jan-19 | 12-Jun-19 | 24-Jun-19 | 196 | 12 | Low | 
MBL Mod 4 | 04-Mar-19 | 20-Aug-19 | 26-Aug-19 | 196 | 6 | Low | 
MBL Mod 5 | 11-Mar-19 | 20-Aug-19 | 02-Sep-19 | 196 | 13 | Low | 
MBL Mod 6 | 06-May-19 | 16-Oct-19 | 21-Oct-19 | 196 | 5 | Low | 
MBL Mod 7 | 13-May-19 | 16-Oct-19 | 28-Oct-19 | 196 | 12 | Low | 
MBL Mod 8 | 01-Jul-19 | 12-Dec-19 | 16-Dec-19 | 196 | 4 | Low | 
MBL Mod 9 | 09-Jul-19 | 12-Dec-19 | 06-Jan-20 | 196 | 25 | Low | 

## Slide 30: Key Deliveries: High Beta Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
HBL-010CRM | 04-May-20 | 01-Jun-20 | 01-Jun-20 | 0 | 0 | Med | 
HBL-020CRM | 01-Jun-20 | 06-Jul-20 | 06-Jul-20 | 0 | 0 | Med | 
HBL-030CRM | 06-Jul-20 | 03-Aug-20 | - | - | - | Med | -
HBL-040CRM | 03-Aug-20 | 07-Sep-20 | - | - | - | Med | -
HBL-050CRM | 07-Sep-20 | 05-Oct-20 | - | - | - | Med | -
HBL-060CRM | 05-Oct-20 | 02-Nov-20 | - | - | - | Med | -
HBL-070CRM | 02-Nov-20 | 07-Dec-20 | - | - | - | Med | -
HBL-080CRM | 07-Dec-20 | 11-Jan-21 | - | - | - | Med | -
HBL-090CRM | 11-Jan-21 | 01-Feb-21 | - | - | - | Med | -
HBL-100CRM | 01-Feb-21 | 01-Mar-21 | - | - | - | Med | -
HBL-110CRM | 01-Mar-21 | 06-Apr-21 | - | - | - | Med | -

## Slide 31: Key Deliveries: High Beta Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
HBL-010LWU | 16-Mar-20 | 16-Mar-20 | 10-Aug-20 | 0 | 147 | Low | 
HBL-020LWU | 20-May-19 | 20-May-19 | 10-Aug-20 | 0 | 448 | Low | 
HBL-030LWU | 20-May-19 | 20-May-19 | 10-Aug-20 | 0 | 448 | Low | 
HBL-040LWU | 20-May-19 | 20-May-19 | 27-Jul-20 | 0 | 434 | Low | 
HBL-050LWU | 20-May-19 | 20-May-19 | 27-Jul-20 | 0 | 434 | Low | 
HBL-060LWU | 20-May-19 | 20-May-19 | 27-Jul-20 | 0 | 434 | Low | 
HBL-070LWU | 01-Jul-19 | 01-Jul-19 | 06-Jul-20 | 0 | 371 | Low | 
HBL-080LWU | 01-Jul-19 | 01-Jul-19 | 06-Jul-20 | 0 | 371 | Low | 
HBL-090LWU | 01-Jul-19 | 01-Jul-19 | 06-Jul-20 | 0 | 371 | Low | 
HBL-100LWU | 01-Jul-19 | 01-Jul-19 | 24-Aug-20 | 0 | 420 | Low | 

## Slide 32: Key Deliveries: High Beta Section
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
HBL-110LWU | 01-Jul-19 | 01-Jul-19 | 12-Aug-19 | 0 | 42 | Med | 
HBL-120LWU | 01-Jul-19 | 01-Jul-19 | 12-Aug-19 | 0 | 42 | Med | 
HBL-130LWU | 05-Aug-19 | 05-Aug-19 | 12-Aug-19 | 0 | 7 | Med | 
HBL-140LWU | 05-Aug-19 | 05-Aug-19 | 02-Sep-19 | 0 | 28 | Med | 
HBL-150LWU | 05-Aug-19 | 05-Aug-19 | 02-Sep-19 | 0 | 28 | Med | 
HBL-160LWU | 05-Aug-19 | 05-Aug-19 | 02-Sep-19 | 0 | 28 | Med | 
HBL-170LWU | 05-Aug-19 | 05-Aug-19 | 23-Sep-19 | 0 | 49 | Med | 
HBL-180LWU | 16-Sep-19 | 16-Sep-19 | 23-Sep-19 | 0 | 7 | Med | 
HBL-190LWU | 16-Sep-19 | 16-Sep-19 | 23-Sep-19 | 0 | 7 | Med | 
HBL-200LWU | 16-Sep-19 | 16-Sep-19 | 18-Nov-19 | 7 | 63 | Med | 
HBL-210LWU | 16-Sep-19 | 16-Sep-19 | 18-Nov-19 | 7 | 63 | Med | 

## Slide 33: HEBT, A2T, DMPL
Relatively flexible installation sequence.
  We can adapt to the inherent delivery changes.
For the HEBT, the main installation driver is the availability of the LWU.
  HEBT beam pipe to be installed in 2018 (early).
    Installation Readiness Review planned soon.
For the DMPL the driver is the Tuning Beam Dump (Target Division delivery)
  Beam Dump System Installed: March 2019
A2T Installation depends on access dates
  A2T is partially part of the Target Building. As things stand, early access to be granted in September 2019.

## Slide 34: HEBT, A2T, DMPL - Installation Timeline
Tunnel
Gallery
2018
2019
2020
2021
ISrc to LEBT
4/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
02/07/18 - 30/11/18
HEBT Spool Pieces (Beam Pipe)
10/12/18 - 19/04/19
HEBT LWUs
22/04/19 - 07/06/19
DMPL LWU
27/05/19 - 27/03/20
DogLeg/A2T LWU

## Slide 35: Key Deliveries: HEBT
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
HEBT-010LWU | 05-Nov-18 | 05-Nov-18 | 18-Nov-19 | 21 | 378 | Low | 
HEBT-020LWU | 05-Nov-18 | 05-Nov-18 | 10-Dec-18 | 21 | 35 | Med | 
HEBT-030LWU | 05-Nov-18 | 05-Nov-18 | 07-Jan-19 | 21 | 63 | Med | 
HEBT-040LWU | 05-Nov-18 | 05-Nov-18 | 14-Jan-19 | 21 | 70 | Med | 
HEBT-050LWU | 05-Nov-18 | 05-Nov-18 | 21-Jan-19 | 21 | 77 | Med | 
HEBT-060LWU | 05-Nov-18 | 05-Nov-18 | 28-Jan-19 | 21 | 84 | Med | 
HEBT-070LWU | 07-Jan-19 | 07-Jan-19 | 04-Feb-19 | 21 | 28 | Med | 
HEBT-080LWU | 07-Jan-19 | 07-Jan-19 | 11-Feb-19 | 21 | 35 | Med | 
HEBT-090LWU | 07-Jan-19 | 07-Jan-19 | 18-Feb-19 | 21 | 42 | Med | 
HEBT-100LWU | 07-Jan-19 | 07-Jan-19 | 25-Feb-19 | 21 | 49 | Med | 
HEBT-110LWU | 07-Jan-19 | 07-Jan-19 | 04-Mar-19 | 21 | 56 | Med | 

## Slide 36: Key Deliveries: HEBT
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
HEBT-120LWU | 07-Jan-19 | 07-Jan-19 | 11-Mar-19 | 21 | 63 | Med | 
HEBT-130LWU | 25-Feb-19 | 25-Feb-19 | 18-Mar-19 | 21 | 21 | Med | 
HEBT-140LWU | 25-Feb-19 | 25-Feb-19 | 25-Mar-19 | 21 | 28 | Med | 
HEBT-150LWU | 25-Feb-19 | 25-Feb-19 | 01-Apr-19 | 21 | 35 | Med | 
HEBT-160LWU | 25-Feb-19 | 25-Feb-19 | 08-Apr-19 | 21 | 42 | Med | 
HEBT-170DV | 19-Aug-19 | 19-Aug-19 | 23-Sep-19 | 0 | 35 | Med | 

## Slide 37: Key Deliveries: DMPL
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
DMPL-010QC | 29-Apr-19 | 29-Apr-19 | 13-May-19 | 21 | 14 | Med | 
DMPL-020QC | 18-Mar-19 | 18-Mar-19 | 06-May-19 | 21 | 49 | Med | 
DMPL-030QC | 18-Mar-19 | 18-Mar-19 | 29-Apr-19 | 21 | 42 | Med | 
DMPL Gamma Blocker | 30-Nov-18 | 30-Nov-18 | 29-Apr-19 | 21 | 150 | Low | 

## Slide 38: Key Deliveries: A2T
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
A2T-010LWU | 29-Apr-19 | 29-Apr-19 | 27-May-19 | 0 | 28 | Med | 
A2T-020LWU | 29-Apr-19 | 29-Apr-19 | 03-Jun-19 | 0 | 35 | Med | 
A2T-030LWU | 29-Apr-19 | 29-Apr-19 | 10-Jun-19 | 0 | 42 | Med | 
A2T-040LWU | 29-Apr-19 | 29-Apr-19 | 17-Jun-19 | 0 | 49 | Med | 
A2T-050LWU | 29-Apr-19 | 29-Apr-19 | 24-Jun-19 | 0 | 56 | Med | 
A2T-060LWU | 10-Jun-19 | 10-Jun-19 | 01-Jul-19 | 0 | 21 | Med | 
A2T-070DV | 19-Aug-19 | 19-Aug-19 | 10-Feb-20 | 0 | 175 | Low | 
A2T-080LWU | 24-Feb-20 | 24-Feb-20 | 02-Mar-20 | 0 | 7 | Med | 
A2T-090LWU | 20-Dec-19 | 20-Dec-19 | 27-Jan-20 | 0 | 38 | Med | 
A2T-100RSM | 20-Dec-18 | 20-Dec-18 | 20-Jan-20 | 0 | 396 | Low | 

## Slide 39: Key Deliveries: A2T
Delivery Item | BL Date (RFI) | Proposed Date (RFI) | Installation Date | Inst. Float (days) | Schedule Risk |  | Overall Risk
 |  |  |  |  | Delivery Float | Risk | 
A2T-110RSM | 20-Dec-18 | 20-Dec-18 | 13-Jan-20 | 0 | 389 | Low | 
A2T-120LWU | 24-Feb-20 | 24-Feb-20 | 02-Mar-20 | 0 | 7 | Med | 
A2T Gamma Blocker | 30-Nov-18 | 30-Nov-18 | 16-Dec-19 | 0 | 381 | Low | 

## Slide 40: Stubs
Successful stub installation test
  Installation sequence produced
  But, installation has not yet started
Mechanical and electrical design work still needed (tooling, cable containment, cable routing, etc.)
  Work underway.
Stub shielding now moved to gallery:
  Simplifies Significantly the stubs installation.
Likely stub installation start: Q3 2018
Courtesy of Mats Pålsson

## Slide 41: Critical Path for Accelerator
The ACCSYS Critical Path to RBOT goes through four intermediate milestones.
The Ion Source to LEBT beam commissioning (Summer 2018) is not on the critical path, but an important transition to initial operations milestone.
2018
2019
2020
2021
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021

## Slide 42
2018
2021
Today
75 days
10 days
15 days
150 days
10 days
60 days
10 days
65 days
180 days
10 days
40 days
10 days
60 days
25 days
65 days
120 days
290 days
290 days
250 days
141 days
50 days
15 days
20 days
20 days
10 days
75 days
20 days
- PSS/SRR
- SC Linac, HEBT, A2T
- NC Linac
- Beam Commissioning
2018
2019
2020
2021
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
17/12/18 - 12/07/19
RFQ + DTL 1 RF System
15/07/19 - 26/07/19
PSS1 Validation
29/07/19 - 18/10/19
RFQ, MEBT, DTL1 RF Conditioning
21/10/19 - 01/11/19
SRR2
04/11/19 - 31/01/20
ISrc to DTL1 Beam Commissioning
27/05/19 - 31/01/20
Full NC Linac RF System
03/02/20 - 14/02/20
PSS1 Re-Validation
17/02/20 - 10/04/20
DTL2, 3, 4 RF Conditioning
13/04/20 - 24/04/20
SRR3
27/04/20 - 17/07/20
ISrc to DTL4 Beam Commissioning
20/07/20 - 21/08/20
DTL5 Installation
03/12/18 - 15/11/19
Elliptical CDS Installation
19/08/19 - 15/11/19
SPK CDS Installation
18/11/19 - 07/08/20
SPK CM Installation
18/11/19 - 01/06/20
MBL CM Installation
01/06/20 - 07/08/20
HBL CM Installation
12/08/19 - 13/12/19
HBL1 LWU Installation
16/12/19 - 27/03/20
A2T LWU Installation
30/03/20 - 19/06/20
MBL/HBL2 LWU Installation
22/06/20 - 14/08/20
SPK LWU Installation
17/08/20 - 25/09/20
Final HBL/SPK LWU Installation
12/08/19 - 25/09/20
SPK RF Power Stations
28/09/20 - 16/10/20
Full PSS Validation
19/10/20 - 13/11/20
DTL5 and SC Linac - Warm RF Conditioning
16/11/20 - 11/12/20
CDS and CMs Cooldown and Tests
14/12/20 - 22/01/21
SC Linac - Cold RF Conditioning
25/01/21 - 05/02/21
SRR4
08/02/21 - 07/05/21
ISrc to DMPL Beam Comm.
10/05/21 - 21/05/21
SRR5

## Slide 43: Near Critical Path
2018
2019
2020
2021
ISrc to LEBT
4/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
Access to A2T Building
16/9/2019
08/07/19 - 26/07/19
PC for MEBT Magnets
07/01/19 - 01/02/19
DTL4
11/03/19 - 05/04/19
DTL1
08/04/19 - 03/05/19
DTL3
10/06/19 - 05/07/19
DTL2
18/11/19 - 13/12/19
HBL-200LWU
18/11/19 - 13/12/19
HBL-210LWU
10/12/18 - 03/05/19
HEBT LWUs
29/04/19 - 07/06/19
DMPL QC
Many more items tracked:
  Subsystems, Utilities, Stub Installation, Cabling Status, ICS, Permits, etc.
  Items will always come on and off critical.

## Slide 44: Assessment and Summary
Major re-baselining effort with significant schedule updates.
  First proton beam at ESS this year (Ion Source and LEBT)
  Beam on Dump (BOD) at 570 MeV with the NC linac, SPK, MBL and two unpowered HBL CMs: February 2021
  Accelerator Ready for Beam on Target (RBOT): May 2021.
  Beam on Target (BOT) date is ~one year later. This margin is to be used as schedule float as well as to install the remaining HB CMs.
Multiple delays accounted for:
  Clear critical path to RBOT.
  Many manufacturing contracts signed, but some are still being prepared, so a certain level of uncertainty remains.
Accelerator utilities installation is run by the infrastructure project
  Matches the accelerator installation plan
  Not on the critical path
Installation will be a major learning curve
  Significant installation load
  Valuable lessons from the FEB, Ion Source and LEBT installations.